LA NKWANTANANG-MADINA MUNICIPAL ASSEMBLY

2025 ANNUAL PROGRESS REPORT

FEBRUARY, 2026

# TABLE OF CONTENTS

TABLE OF CONTENTS	i

LIST OF ACRONYMS	iv

EXECUTIVE SUMMARY	vii

CHAPTER ONE	1

1.0 INTRODUCTION	1

1.1 PURPOSE OF THE  2025 MONITORING AND EVALUATION (M&E) UNDERTAKEN	2

1.2 STATUS/SUMMARY OF ACHIEVEMENTS OF THE IMPLEMENTATION OF DMTDP	4

1.3 DETAILS ON THE ANNUAL ACTION PLAN (AAP) IMPLEMENTED	4

1.4 PROPORTION OF THE DMTDP IMPLEMENTED	6

1.5 CHALLENGES ENCOUNTERED IN IMPLEMENTATION OF THE MTDP	7

1.6 PROCESSES INVOLVED	7

CHAPTER TWO	9

2.0 INTRODUCTION	9

2.1.1 PROGRAMME AND PROJECT STATUS FOR 2025	9

2.1.2 TOTAL NUMBER OF ACTIVE PROJECTS	15

2.1.3 DISTRIBUTION OF PHYSICAL PROJECTS OF THE ASSEMBLY	16

2.1.4 PROJECT AGE ANALYSIS	16

2.1.5 REPAIR AND MAINTENANCE OF EXISTING INFRASTRUCTURE	18

2.1.6 PROGRAMME REGISTER FOR 2025	20

2.2 UPDATE ON DISBURSEMENT FROM FUNDING SOURCES (GH¢)	22

2.2.1 UPDATE ON DISBURSEMENT	25

2.2.2 ASSEMBLY’S CAPEX BUDGET PERFORMANCE ANALYSIS	26

2.2.3 CAPEX BUDGET ALLOCATIONS AND IMPLEMENTATION FOR ACTIVE PROJECTS	28

2.2.4 CUMULATIVE CAPEX THROW FORWARD AND MTBF ENVELOPE 2025-2027	32

2.2.5 AMOUNT OF CAPITAL ENVELOPE SPENT ON ACTIVE PROJECTS	33

2.2.6 ESTIMATED COST AND COST OVERRUNS OF ACTIVE PROJECTS	33

2.3 UPDATE ON INDICATORS AND TARGETS	34

2.3.1. Development Dimension: Economic Development	42

2.3.2 Development Dimension: Social Development	44

2.3.3 Development Dimension: Environment, Infrastructure and Human Settlements	47

2.3.4 Development Dimension: Governance, Corruption and Public Accountability	48

2.3.5 Development Dimension: Emergency Planning and COVID-19 Response.	49

2.3.6 Development Dimension: Implementation, Co-ordination, Monitoring and Evaluation	50

2.4 UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES FOR 2025	51

2.4.1 STAFF STRENGTH OF THE ASSEMBLY	52

2.4.2 CAPACITY DEVELOPMENT (Annex 7c: Capacity Development)	57

2.4.3 LOGISTICS ANALYSIS	58

2.5 REPORT ON CRITICAL DEVELOPMENT AND POVERTY ISSUES	60

2.5.1 LIVELIHOOD EMPOWERMENT AGAINST POVERTY (LEAP)	60

2.5.2 NATIONAL YOUTH EMPLOYMENT PROGRAMME BEING IMPLEMENTED THROUGH THE YOUTH EMPLOYMENT AGENCY (YEA)	60

2.5.3 CAPITATION GRANT	60

2.5.4 FREE SENIOR HIGH SCHOOL PROGRAMME	61

2.5.5 SUPPORT TO PERSONS WITH DISABILITIES (PWDS) - PWDs COMMON FUND SUPPORT/UTILISATION)	61

2.5.6 NATIONAL HEALTH INSURANCE SCHEME (NHIS)	62

2.5.7 GHANA SCHOOL FEEDING PROGRAMME (GSFP)	62

2.5.8 PLANTING FOR FOOD AND JOBS (PFJ) PROGRAMME	63

2.5.9 YOUSTART GHANA JOBS AND SKILLS PROJECT	63

2.5.10 STREET NAMING AND PROPERTY ADDRESSING SYSTEM (SNPAS)	63

2.5.11 DISSEMINATION OF THE CO-ORDINATED PROGRAMME OF ECONOMIC AND SOCIAL DEVELOPMENT POLICIES (CPESDP) 2017-2024	63

2.5.12 IMPLEMENTATION OF THE NATIONAL ANTI-CORRUPTION ACTION PLAN (NACAP)	64

2.5.13 MUNICIPAL HIV AND AIDS RESPONSE	64

2.5.14 IMPLEMENTATION OF 2024 GREATER ACCRA RESILIENT AND INTEGRATED DEVELOPMENT (GARID) PROJECT OPERATION AND MAINTENANCE WORKPLAN (DRAINAGE LOGISTICS PROCUREMENT, DRAINAGE CONDITION ASSESSMENT, DESILTING WORK ETC. UNDER THE GARID PROJECT.	65

2.5.15 THE UNICEF-SUPPORTED INTEGRATED SOCIAL SERVICES (ISS) DELIVERY PROGRAMME	65

2.6 EVALUATION AND PARTICIPATORY MONITORING AND EVALUATION	67

2.6.1 UPDATE ON EVALUATION CONDUCTED	67

2.6.2 PARTICIPATORY MONITORING AND EVALUATION	69

2.6.3 UPDATE ON PARTICIPATORY M&E	70

CHAPTER THREE	72

3.0 INTRODUCTION	72

3.1 KEY ISSUES ADDRESSED AND THOSE YET TO BE ADDRESSED	72

3.2 RECOMMENDATIONS	72

3.3 CONCLUSION	73

APPENDIX 1	74

# LIST OF ACRONYMS

AIDS                            	Acquired Immune Deficiency Syndrome

BMS	                        	Biometric Membership Solutions

CAPBUSS                     	Coronavirus Alleviation Programme Business Support Scheme

CBO		           		Community Based Organisation

CETA                            	Community Education Teaching Assistants

CHMCs                         	Community Health Management Committees

CHW		          		Community Health Worker

CPA		         		Community Policing Assistant

DACF		         		District Assemblies Common Fund

DCPP                            	District Child Protection Programme

DDF                              	District Development Facility

DMTDP                       	District Medium-Term Development Plan

DPCU                           	District Planning Co-ordinating Unit

DRIP		       		District Road Improvement Project

DSWCD                       	Department of social Welfare and Community Development

E-HEALTH	        		Electronic Health

GARID		       	Greater Accra Resilient and Integrated Development Project

GEA		       		Ghana Enterprises Agency

GETFund 	        		Ghana Education Trust Fund

GHS		       		Ghana Health Service

GLST		        		Ghana Luxembourg Social Trust

GoG		        		Government of Ghana

GSFP                            	Ghana School Feeding Programme

GSGDA                        	Ghana Shared Growth Development Agenda

GSOP                           	Ghana Social Opportunities Project

HIV                               	Human Immuno-Deficiency Virus

IGF                               	Internally Generated Funds

ISS                                	Integrated Social Services

ISSOP		        		Integrated Social Services Operating Procedures

LEAP                            	Livelihood Empowerment Against Poverty

MAC                            	Municipal AIDS Committee

M&E                            	Monitoring and Evaluation

NABCO                        	Nation Builders Corps

NDPAS                        	National Digital and Property Address System

NDPC                          	National Development Planning Commission

NEIP		       		National Entrepreneurial and Innovation Programme

NHIA                           	National Health Insurance Authority

NHIS                            	National Health Insurance Scheme

NGOs                          	Non-Governmental Organisations

NHIS                           	National Health Insurance Scheme

NYEA	                      		National Youth Employment Agency

OPD		       		Out-Patient Department

OVC		       		Orphans and Vulnerable Children

PFJ		       		Planting for Food and Jobs

PPEs                          		Personal Protective Equipment

PLWHA                        	People Living With HIV and AIDS

PMTC                          	Prevention from Mother to Child

POS                              	Point of Sale

PWDs                          	Persons with Disabilities

RCC                              	Regional Co- ordinating Council

RHC 		        		Residential Home for Children

RIAP		        		Revenue Improvement Action Plan

SGBV		       		Sexual and Gender-Based Violence

SME                             	Small and Medium Enterprises

UNICEF                        	United Nations International Children and Education Fund

YCS		        		Youth in Coastal Sanitation

YEP	                       		Youth in Environmental Protection

YIFS	                        	Youth in Fire Service

YIPS	                         	Youth in Prison Service

# EXECUTIVE SUMMARY

Monitoring and Evaluation (M&E) is an indispensable tool for measuring the implementation of development programmes and projects the world over. This development practice applies to the implementation of development interventions in Metropolitan, Municipal and District Assemblies (MMDAs) in Ghana.

It is in furtherance of this that the National Development Planning Commission has directed MMDAs to prepare and submit Quarterly M&E, and Annual Progress Reports to keep it abreast of the progress of implementation of their respective programmes and projects which collectively define the country’s status as far as development is concerned.

This 2025 Annual Progress Report has therefore been prepared through participatory processes from the assessment of the status of indicators and targets formulated for rolling out of the various development interventions planned for 2025.

This 2025 Progress Report is presented in three (3) chapters. Chapter one provides a comprehensive overview of key monitoring and evaluation objectives for 2025, processes followed in the M&E as well as difficulties encountered and status of implementation of the DMTDP 2022-2025 whilst chapter two reviews the programme and project status for the year vis a vis financial disbursements for the implementation of the various programmes and projects, and an update on critical development and poverty issues with some insight into the participatory M&E methods employed in tracking and evaluating the interventions.

Chapter three on the other hand, highlights key issues addressed and those yet to be addressed in the context of the implementation of programmes and projects during the year with appropriate recommendations and conclusion.

It is envisaged that stakeholders will sustain the commitment demonstrated to create the enabling environment for optimal implementation of planned programmes and projects for 2025 and beyond.

# CHAPTER ONE

## 1.0 INTRODUCTION

The La Nkwantanang-Madina Municipal Assembly (LaNMMA), created on March 15, 2012 by Legislative Instrument (LI) 2131 is one of the 29 Assemblies in the Greater Accra Region of Ghana. It is located 15km on the north-east of Accra, the national Capital of Ghana. The Municipality shares boundaries with Akwapim South District  Assembly to the North,  Kpone Katamanso Municipal Assembly to the North-East,  Ga East Municipal Assembly to the West; Adentan Municipal Assembly to the East and Ayawaso West  Municipal Assembly to the South.

The population of the Municipality in 2025 is estimated at 248,335. This comprise of 121,684 males representing 49% and 126,651 Females representing 51%. These consist of Ghanaians and other foreign nationals resident or visiting temporarily to pursue business interests. About 84% of the population of the Municipality resides in urban localities. The Municipality’s huge population presents vast economic advantages and challenges. The sheer population size of the Municipality unleashes pressure on existing social facilities and services, hence the need for expansion of infrastructure and related social services.

Since the adoption of the decentralization policy by the Government of Ghana in 1988 with  the subsequent constitutional backing from the 1992 Constitution and relevant laws with Local Government Act, 2016 (Act 936), National Development Planning (System) Regulations, 2016, LI 2232  being some current examples), District Assemblies have been invested with the mandate to develop, implement, monitor and evaluate plans  in a participatory fashion to guide  development in their respective areas of jurisdiction premised on a formulated development policy framework of Government. This 2025 Annual Progress Report is thus prepared in the context of Agenda for Jobs II:   (2022-2025) which broadly aims to: create opportunities for all Ghanaians, Safeguard the natural environment and ensure a resilient, built environment, maintain a stable, united and safe society; and build a prosperous society.

The five principal thematic areas of the Policy framework include:

- Economic Development

- Social Development

- Environment, Infrastructure and Human Settlements

- Governance, Corruption and Public Accountability

- Emergency Planning and COVID-19 Response

- Co-ordination, Monitoring and Evaluation.

Through the medium of the Assembly’s Monitoring and Evaluation Plan (M&E) which is geared towards efficiency, effectiveness, impact, acceptability and Value for money in project execution, the entire 181 programmes and projects (earmarked for implementation in the 2025 Annual Action Plan were all implemented. This represents 100%) which is a component of the Municipal Medium-Term Development Plan (2022-2025) were rolled out. It must however be emphasized that not all implemented programmes and projects were completed.

## 1.1 PURPOSE OF THE 2025 MONITORING AND EVALUATION (M&E) UNDERTAKEN

The main purpose of undertaking the 2025 Monitoring and Evaluation (M&E) was to afford the District’s Development Actors (ie. Stakeholders) the opportunity to ascertain at first-hand whether or not projects inputs being allocated by the Assembly were being utilized appropriately and were producing the intended results in a sustainable manner. It was to further find out whether or not completed programmes and projects were serving the intended purpose.

The specific purpose of the M&E conducted for period were:

- To apply relevant indicators and targets in the context of the goals and objectives outlined in the MTDP to measure progress.

- To comply with existing legal requirements (including the 1992 Constitution, Act 936 of 2016, LI 2232 of 2016 etc.).

- To enhance effective and efficient performance of the Assembly in its bid to achieve defined goals and objectives of the Assembly.

- To help track progress in the implementation of programmes and projects in order to inform decision-making.

- To identify and assess various stakeholders who could affect or be affected by the outcome of the planned interventions enshrined in the MTDP. The M&E was meant to provide medium of communication to prescribe roles and responsibilities of the relevant stakeholders.

- To use the M&E process to gather, analyse and use good quality data in furtherance of   preparation and implementation of other development plans of the Assembly.

- To interact with a wider stakeholder both internally and externally to expand the space for an enhanced stakeholder participation in the development process of the Assembly.

- To make recommendations for the pursuit of corrective actions to improve service delivery in the Municipality.

The report thus highlights programmes and projects implemented between January – December, 2025 and achievements recorded over the period as derived from the Municipal Medium-Term Development Plan (2022-2025). The report is divided into two principal components. The first segment comprised of a general introduction, the vision and mission statements of the Assembly.  It also provides a brief background to the report, objectives and the general layout of the report. The second part outlines the monitoring activities carried out, discusses the progress made as well as achievements chalked by the Assembly in 2024 and concludes with an update of major programmes implemented in the Municipality.

A combination of participatory processes and methodologies were adopted in the course of implementing the planned programmes and projects for the year under review.  Highlights of some of the methods employed include the following:

Monitoring

- Holding of monthly Site Meetings

- Holding of Stakeholder Meetings to design checklist

- Conduct of Quarterly Field Monitoring Visits by Stakeholders

- Organisation of Quarterly MPCU Meetings

- Holding of Quarterly Stakeholder Review Meetings

- Collation and review of reports from decentralized Departments of the Assembly and   Civil Society Organisations.

Evaluation

Evaluation of the implemented programmes and projects from the Plan was also conducted as follows:

- End of year holistic reviews of programmes and projects

- End of year reviews of selected projects

- The M&E conducted over the period brought to the fore notable successes and challenges which are enumerated in the latter part of this report.

## 1.2 STATUS/SUMMARY OF ACHIEVEMENTS OF THE IMPLEMENTATION OF DMTDP

For the year under review, the Assembly earmarked 181 programmes and projects for implementation. At the end of the year, all 181 planned programmes and projects were successfully rolled-out. This represents 100% progress. This however does not translate into full completion of the interventions executed.  Comparatively, the physical interventions implemented during the period were relatively small compared to the non-physical ones. A number of strategies have been deployed by stakeholders to enhance performance in the implementation of planned programmes and projects the subsequent years.

## 1.3 DETAILS ON THE ANNUAL ACTION PLAN (AAP) IMPLEMENTED

Annex 2a: Details on the Annual Action Plan (AAP) Implemented

| S/N | Development Dimension | 2022 |  | 2023 |  | 2024 |  | 2025 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Plan | Executed | Plan | Executed | Plan | Executed | Plan | Executed |
| 1 | Economic Development | 30 | 27 | 28 | 27 | 31 | 31 | 35 | 35 |
| 2 | Social Development | 62 | 61 | 33 | 30 | 50 | 50 | 64 | 64 |
| 3 | Environment, Infrastructure and Human Settlements | 53 | 50 | 32 | 31 | 35 | 35 | 43 | 43 |
| 4 | Governance, Corruption and Public Accountability | 17 | 17 | 11 | 11 | 14 | 14 | 22 | 22 |
| 5 | Emergency Planning and COVID-19 Response | 9 | 8 | 5 | 4 | 4 | 4 | 4 | 4 |
| 6 | Implementation, Co-ordination, Monitoring and Evaluation | 12 | 11 | 8 | 8 | 13 | 13 | 13 | 13 |
|  | Total | 183 | 174 | 117 | 111.3 | 147 | 147 | 181 | 181 |

Source: LaNMMA MPCU, 2025

Analysis of Planned Activities for 2025 and Actual Activities Executed under the Prescribed Development Dimensions

Annex 2a principally focuses on the planned activities for 2025 and those that were actually executed under the prescribed development dimensions. For the period under review, the Assembly approved for implementation a total of 181 activities, all 181 approved interventions were carried out as against 147 executed for 2024. Breakdown of the total activities for 2025 and the corresponding actual roll-out details are as follows: Economic Development (planned 35, implemented 35), Social Development (planned 64, implemented 64), Environment, Infrastructure and Human Settlements (planned 43,implemented 43), Governance, Corruption and Public Accountability (planned 22, implemented 22), Emergency Planning and COVID-19 Response (planned 4, Implemented 4), Implementation, Co-ordination, Monitoring and Evaluation (planned 13, implemented 13).

Success Factors

The success factors for the outstanding achievements are as follows:

- Improved cash-flow arising out the substantial increase in the District Assemblies’ Common Fund (DACF) and its timely release. Consequently, contractors and Departments working for the Assembly were better resourced to deliver on the assignments entrusted to them.

- Strengthening of the project monitoring mechanism at the Assembly through logistical provision and timely release of funds stimulated the monitoring process for better results.

- Support from the road agencies and Government’s policy initiatives including the District Road Improvement Project (DRIP) with its accompanying set of road construction equipment has been encouraging during the year as compared to previous years.  The condition of some critical access roads in communities such as Teiman Community Roads as well as the Oyarifa Town Roads were remarkably improved.

Successes Chalked and relationship to the Goals and Objectives Set by the Assembly

The activity implementation successes achieved has translated into improved service delivery in sanitation, education, health, road, energy among others. The cumulative impact of these was fulfilment of the goals and objectives set by the Assembly in its MTDP.

## 1.4 PROPORTION OF THE DMTDP IMPLEMENTED

Annex 2b:  Proportion of the DMTDP Implemented

| Indicators | Baseline 21 | Actual 22 | Actual 2023 | Target 2024 | Actual 2024 | 2025 Target | 2025 Actual |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Proportion of the Annual Action Plans Implemented by the end of the year: - Percentage completed - Percentage of ongoing Interventions - Percentage of Interventions Abandoned - Percentage of Interventions yet to start | 95% 85% 9% 0% 1% | 100% 92% 4% 1% 3% | 95.1% 89% 6.1% 0% 0% | 100% 100% 0% 0% 0% | 100% 96% 4% 0% 0% | 100% 100% 0% 0% 0% | 100% 78% 22% 0% 0% |
| - Proportion of the Overall Medium-Term Development Plan Implemented | 65% | 23% | 25% | 22% | 25% | 30% | 25% |

Source: LaNMMA MPCU, 2025

Analysis of DMTDP Implementation in Relation to Goals and Objectives

As depicted in the preceding table, there is no percentage difference between the implementation of the Assembly’s planned programmes and projects, and the actual performance. This portrays a precision of the Assembly’s development forecast and achievement of the objectives set.

Success Factors

The remarkable performance is attributable to a combination of factors which include but not limited to following:

- Improvement in the DACF transfers that increased from GHC 1,411,384.13 in 2024 to GHC 20,900,161.20 in 2025 coupled with an impressive Internally Generated Funds (IGF)   collection of 14,071,899.52 The effective RIAP (including institution of weekly revenue performance League Table with the associated reward and sanction regime etc.) did the trick.

- The strengthening of the Assembly’s M&E system through beefing up of the Assembly’s fleet of vehicles in the previous year tremendously helped in stepping up monitoring of on-going works under implementation for expeditious execution and completion.

The effective and efficient execution of 100% of the Assembly’s Action Plan for 2025 largely contributed to improving service delivery in the Municipality in tandem with the goals and objectives set by the Assembly.

## 1.5 CHALLENGES ENCOUNTERED IN IMPLEMENTATION OF THE MTDP

The difficulties encountered by the Assembly in the implementation, monitoring and evaluation of the approved action plan for 2025 included:

- Slight drop in IGF revenue due to termination of the contract with a third party company for the collection of Property rates and the delay in getting the new government approved revenue system implemented.

- Weak institutional and Departmental collaboration adversely affecting the accession of relevant data in real time particularly from the decentralised Departments of the Assembly.

- Delay in release of logistics such as vehicles to Departments and Officers of the Assembly by Management for implementation, monitoring and evaluation of planned interventions.

- Delay in releasing funds to undertake monitoring and evaluation activities

- Litigation on lands earmarked for implementation of approved etc.

- Poor road conditions in some parts of the Municipality affecting mobility and for field activities.

- Growing apathy on the part of community members or the citizens towards participation in monitoring and evaluation.

## 1.6 PROCESSES INVOLVED

The process of preparing the 2025 Progress Report was a collaborative one. It involved the application of qualitative, quantitative and other participatory techniques (e.g. questionnaire, focus group discussion). Highlights of the process for the conduct of the monitoring and evaluation were as follows:

- Constitution of a combined monitoring   team consisting of Heads of Decentralised Departments, Non-Governmental Organisations (NGOs), Civil Society Organisations (CSOs), User Institutions of the Projects, Chiefs, Queen-mothers, Opinion Leaders; Assembly Members, Women Groups, and Community Members/End Users of the Projects. The community–level team members were meticulously selected from the project communities or catchment areas with gender lenses for data collection as well as regular site meetings to assess progress of work with a view to propose remedial actions where necessary.

- Contractors and some of the vulnerable groups from across the communities such as Persons with Disabilities (PWDs) also featured, alongside Development Partners in the monitoring undertaken during the year in the gathering of relevant data and consensus building for effective and efficient implementation of the 2024 Annual Action Plan (AAP).

- Data for the report was elicited from both primary and secondary sources.  These include: questionnaire administration, focus group discussion, monitoring visits, appraisal of reports from Decentralised Departments, review of presentations made at the various MPCU Meetings etc. The data collected was collated, cross-checked and confirmed by stakeholders at a Stakeholders’ Review Meeting before being incorporated into the report.

# CHAPTER TWO

## 2.0 INTRODUCTION

This chapter basically highlights the status of implementation, monitoring and evaluation of programmes and projects in the DMTDP.

### 2.1.1 PROGRAMME AND PROJECT STATUS FOR 2025

Status of programmes and projects for 2025 are indicated in Annex 4a below:

Annex 4a: Project Register for 2025

| Project Description |  | Development Dimension | Location | Contractor | Contract Sum | Date of Award | Source of Funding | Date Started | Expected Date of Completion | Expenditure to Date | Outstanding Balance | Implementation Status |  | Strategies to Improve Project Completion Rate | How Citizens were Involved in Monitoring of Woks Contract | Remarks Summary on Land Acquisition and Resettlement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Code | Name |  |  |  |  |  |  |  |  |  |  | % | Picture |  |  |  |
| SECTOR: EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 001 | Construction of 1No. 5-Unit KG Block with Ancillary Facilities for Fire Armour Basic School | Social Development | Madina | M/s Mohd Awal Investment Ltd | 549,200.00 | 12/10/23 | DACF | 19/10/23 | 19/06/24 | 250,000.00 | 299,200.00 | 100% |  | Termination of Contract and initiation of process for re-award of Project through due process | Participatory Field Monitoring, Site Meetings | Land is legally acquired by the Assembly and Ghana Education Service |
| 002 | Construction of 1No. 3-Storey 18-Unit Classroom Block with Ancillary Facilities for Pantang Hospital Basic School (Phase 1: Construction of 1No. 6-Unit Classroom Block) | Social Development | Pantang | M/s City Plus Ltd | 2,379,224.00 | 31/12/25 | DACF | 05/01/26 | 31/08/26 | - | - | 45% |  | Facilitation of payment to the contractor | Participatory Field Monitoring, Site Meetings | Land is legally acquired by the Assembly and Ghana Education Service from Pantang Hospital Authorities |
| 003 | Procurement and Distribution of Assorted School Furniture to Selected 1st and 2nd Cycle Schools | Social Development | Legon PRESEC, West Africa Senior High School etc. | M/s …. | - | …2025 | DACF | ….2025 | …2026 | - | - | 70% |  | Follow up on last consignment of furniture yet to be supplied | Stakeholder Engagement in the Procurement and Distribution Process | - |
| SECTOR: ECONOMY/LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 004 | Construction of 2No. 18-Unit 3-Storey Retail Shops and 2 No. 24-Unit Market Sheds at Madina Market (Phase 2) | Economic Development | Madina | M/s Amaa Integrated Ltd. | 13,501,251.94 | 10/08/224 | DACF | 20/08/24 | 30/04/202 | 12,953,321.94 | 547,930.00 | 75% |  | Facilitating payment of certificated for work done | Participatory Field Monitoring, Site Meetings | Land is legally acquired by the Assembly through the Bethlehem Congregation of Presbyterian Church of Ghana |
| SECTOR: GOVERNANCE/DECENTRALIZATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 004 | Construction of 1No. 3-Storey Office Accommodation with Conference Hall and Ancillary Facilities for Oyarifa Zonal Council (Phase 1) | Governance, Corruption and Public Accountability | Oyarifa | M/s City Plus Ltd. | 2,402,577.70 | 31/12/25 | DACF | 06/01/2026 | 31/08/26 | - | - | 25% | - | Engaging with contractor to resolve possible challenges | Participatory Field Monitoring, Site Meetings | Land is legally acquired by the Assembly through the Bethlehem Congregation of Presbyterian Church of Ghana |
| SECTOR: ENERGY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 005 | Maintenance and installation of Streetlights in the Municipality | Environment Infrastructure and Human Settlements | Municipal-wide | M/s Bussak Reign Ltd. | 194,200.00 | 04/03/25 | IGF | 14/03/25 | 30/05/2025 | 194,2000.00 | - | 100% |  | - | Stakeholder Engagement in the Procurement and Distribution Process | - |
| SECTOR: ROAD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 006 | Installation of 500m Length of Wire Mesh Protection Fence Along Madina Zongo Junction Stretch of the N4 Road | Environment Infrastructure and Human Settlements | Madina (Zongo Jnc.) | M/s Blue Naak’s Co. Ltd | 548,637.50 | 10/12/25 | DACF | 17/12/25 | 18/03/26 | 400,000.00 | 148,637.50 | 80% |  | Facilitate payment due contractor for work done. for | Stakeholder Engagement in the Enforcement of the Use of Footbridges | - |
| 007 | Gravelling and Spot Improvement of Selected Roads in the Municipality | Environment Infrastructure and Human Settlements | Oyarifa,Madina, Teiman (Burger Town, Station Road, High Tension, Ghana Flag, Nkwantanang Chief’s Palace etc. | M/s Chabb099 Construction Works, M/s Markskan Ltd., M/s Bussak Reign Ltd. | 840,159.20 | 02/07/25, 03/02/25 | DACF | 15/07/25 | 04/08/25 03/10/2025 | 526,968.80 | 313,190.40 | 100% |  | Facilitate payment for work done. | Stakeholder Engagement in the selection and improvement of the roads concerned | - |
| 008 | Construction of 1.2 Pipe Culvert at Sakora – West Adenta | Environment Infrastructure and Human Settlements | Sakora (West Adenta) | M/s Markskan Ltd. | 154,795.00 | 20/06/25 | IGF | 02/07/25 | 03/10/25 | 127,181.25 | 27,613.75 | 100% |  | - | Stakeholder Engagement in the selection and improvement of the roads concerned |  |
| 009 | Desilting of Drains and Culverts at Raidul Jannah Mosque | Environment Infrastructure and Human Settlements | Madina (Zongo) | M/s Chabb099 Constrution Works | 25,580.00 | 10/02/25 | DACF | 24/02/25 | 23/05/25 | 25,378.00 | 202.00 | 100% |  | - | Stakeholder Engagement in the selection and improvement of the roads concerned |  |

Source: LaNMMA, MPCU 2025

Analysis of DMTDP Implementation in Relation to Goals and Objectives set by the Assembly

Annex 4a (The Project Register) presents details of the physical projects implemented by the Assembly in 2025. In all, a total of 9 physical projects spread across health, education, road, sanitation, energy, governance and host of other sectors were successfully implemented. All 9 projects were directly awarded by the Municipal Assembly. Five out of the 9 physical projects were completed. The remaining 4 are at various levels of completion and have accordingly be rolled over to 2026 for completion to serve the intended purpose.

Success Factors

The notable successes chalked in the physical projects execution and completion rate by necessitated by a variety of factors including the following:

- Strict implementation of the Assembly’s Revenue Improvement Action Plan (RIAP) and the resultant improvement in Internally Generated Funds collection of GHC 14, 071,899.52 and the substantial transfer from the DACF of GHC 20,900,000,161.21.strategically positioned the Assembly to meet its budgetary obligations and payment commitments.

- The stepping-up of the implementation Assembly’s Monitoring and Evaluation (M&E) activities and retooling of the M&E Team with the procurement of two new pick-ups also provided a boost to the project implementation and the significant achievement.

The effective roll-out of 9 physical projects and completion of 5 within the year to a very large extent enabled the Assembly to realize its goals and objectives of improving quality service delivery to the people of the Municipality.

The inability of the GARID Project Secretariat to transfer sanitation and drainage maintenance grant to the Assembly affected the completion of some interventions.

### 2.1.2 TOTAL NUMBER OF ACTIVE PROJECTS

Annex 4a. 1: Total Number of Active Projects

| Development Dimension | Physical Projects in the Municipality |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rollover Projects from Previous Years |  |  | Approved New Projects Introduced in the Year |  |  |  |  |
|  | 2022 | 2023 | 2024 | 2022 | 2023 | 2024 | 2025 |  |
| Economic Development | - | 1 | 1 | - | 11 | 4 | 0 | 15 |
| Social Development | 1 | 1 | 1 | 7 | 2 | 6 | 1 | 16 |
| Environment/Infrastructure/ Human Settlements | 2 | 3 | 3 | 8 | 12 | 9 | 2 | 23 |
| Governance/Corruption/ Public Accountability | - | - | 1 | 5 | 6 | 2 | 1 | 14 |
| Emergency | - | - | - | - | - | - | 0 | - |
| ICME | - | - | - | - | - | - | 0 | - |
| Total | 3 | 5 | 6 | 20 | 31 | 21 | 4 | 68 |

Source: LaNMMA MPCU, 2025

Analysis of Assembly’s Performance in Relation to Active Physical Projects Rolled-Over and Approved for Completion

From 2022, a number of planned projects across all the Development Dimensions that had not seen light of day were re-prioritized for completion in the subsequent years. Unfortunate as it might be, the situation pushed the Assembly in 2024 to work on the backlog and reduce the list, if not clear them completely. In 2025 however, 4 projects had to be rolled over due to delayed transfer of statutory funds and late award of projects.

Success Factors

The progress recorded in respect of the above was largely propelled by strict enforcement financial discipline in expenditure.

The achievement made contributed to the Assembly’s enhanced public image.

### 2.1.3 DISTRIBUTION OF PHYSICAL PROJECTS OF THE ASSEMBLY

Annex 4a. 2: Distribution of Physical Projects Among Departments of the Assembly

| Departments | No. of Projects |  | Total | Collaborating MDA |
| --- | --- | --- | --- | --- |
|  | Rollover | New |  |  |
| Education | 1 | 1 | 1 | GES |
| Health Department | 1 | - | 0 | GHS |
| Environmental Health Unit | 8 | 1 | 0 | MLGC&RA |
| Department of Urban Roads | 1 | 6 | 2 | DUR |
| Governance/ Decentralization | 0 | 0 | 1 | Zonal Council |

Source: LaNMMA DUR, 2025

Annex 4a.2 outlines the distribution of physical projects among the Departments of the Assembly.

This table provides insights into the Departments with the most pressing developments needs and gaps, hence the prioritization of resource allocation and interventions to possibly address the development deficit.

### 2.1.4 PROJECT AGE ANALYSIS

Annex 4a. 3: Project Age Analysis

| Project Age | No. of Projects | Time Overruns (In Years and Months) | Cost Overruns | Completion Status |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Average Completion Rate (%) | Highest (%) | Least (%) |
| Projects that are 20 years but less than 24 years | - | - | - | - | - | - |
| Projects that are 11 years but less than 18 years | - | - | - | - | - | - |
| Projects that are 10 years but less than 11 years | - | - | - | - | - | - |
| Projects that are 9 years but less than 10 years | - | - | - | - | - | - |
| Projects that are 8 years but less than 9 years | - | - | - | - | - | - |
| Projects that are 7 years but less than 8 years | - | - | - | - | - | - |
| Projects that are 6 years but less than 7 years | - | - | - | - | - | - |
| Projects that are 5 years but less than 6 years | - | - | - | - | - | - |
| Projects that are 4 years but less than 5 years | - | - | - | - | - | - |
| Projects that 3 years but less than 4 years | - | - | - | - | - | - |
| Projects that are 2 years but less than 3 years | - | - | - | - | - | - |
| Projects that are 1 year but less than 2 years | 11 | 1yr | - | 100% | 100% | 100% |
| Projects that are 0 years but less than 1 year | - | - | - | - | - | - |
| Total Projects | 11 | 1yr | - | 100% | 100% | 100% |

Source: LaNMMA MPCU, 2025

Annex 4a.3 has focus on analyzing the projects implementation duration and possible delays for prompt action. Interestingly, none of the projects that featured over the period had more than one year time overrun. This is a healthy practice that could be improved upon in subsequent years.

### 2.1.5 REPAIR AND MAINTENANCE OF EXISTING INFRASTRUCTURE

Annex 4b: Repair and Maintenance of Existing Infrastructure

| Asset/Infrastructure | Location | Type of Maintenance | Estimated Cost | Actual Release | Gap | Expenditure | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Repair of School Building Roofs | Madina No. Cluster of School, PRESEC Basic School, Nkwantanang Basic School etc. | Roof Repairs | 750,000.00 | 400,000.00 | 350,000.00 | 400,000.00 | That budgetary allocation for repair and maintenance of public infrastructure be increased to protect public assets and ensure longer lifespan |
| Construction of 1.2m pipe culverts at Sakora (West Adenta) | Sakora (West Adenta) | Maintenance of Culvert | 170,000.00 | 127,181.25 | 42,818.75 | 127,181.25 | That the bridge be maintained regularly to avert severe deterioration |
| Grading/Gravelling ,Reshaping and Spot Improvement of 19km Length of Selected Community Roads | Teiman, Oyarifa, Madina etc | Grading, Gravelling, Reshaping and Spot Improvement | 900,159.20 | 526,968.00 | 373,190.4 | 526,968.80 | That budgetary allocation for repair and maintenance of public infrastructure be increased to protect public assets and ensure longer lifespan |
| Desilting of Drain and Culvert at Raidul Jannah Mosque | Madina Raidul Jannah Mosque | Desilting of Drain | 30,000.00 | 25,378.00 | 4,622.00 | 25,378.00 | That budgetary allocation for repair and maintenance of public infrastructure be increased to protect public assets and ensure longer lifespan |

Source: LaNMMA, Finance Department, 2025

Analysis of Assembly’s Performance in Relation to Repair and Maintenance of Existing Public Infrastructure under Assembly’s Jurisdiction

Effective running of an organization requires human, financial and material resources. The right mix of personnel and availability of material resources ensure optimum performance in relation to the set objectives of the organization concerned. To achieve this, identification of the material resource base and financial resources as well as planning for their operations and maintenance are critical in the realization of the collective objectives of the organization. In recognition of this, the Assembly has over the years been planning and budgeting for Operation and Maintenance on annual basis. The year 2025 was no exception. Unfortunately however, there has been a funding gap over the years.

For the year under review there was a total budget of GHC 1,850,159.20 for operation and maintenance .Out of this, only GHC 1,079,527.25 was utilized. The Assembly performed creditably as far as repair and maintenance of public infrastructure are concerned.

Success Factors

The success factor for the achievement made under the repair and Maintenance of infrastructure under the control of the Assembly were:

- The obligation to fulfil the service delivery demands of the Assembly’s rate-payers (ie. the citizenry) who persistently honour their rate payment responsibility to the Assembly.

Factors for Failure

The non-release of the GARID O&M Grant for 2025   affected the full realization of the goals and objectives for infrastructure maintenance full repairs programmed for the year.

Extent of Successes and Failures on the Attainment of Goals and Objectives set by the Assembly

The non- release of the GARID Grant support for infrastructure maintenance was serious shortfall to the Assembly in 2025. The Assembly solely   financed the O&M activities from its IGF.

### 2.1.6 PROGRAMME REGISTER FOR 2025

Annex 4c: Programme Register for 2025

| PROGRAMME DESCRIPTION | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | AMOUNT INVOLVED (SUM GHC) | SOURCE OF FUNDING | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS |  | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | % | Pictures |  |
| Planting for Food and Jobs (PFJ) | Economic Development | 1,500.00 | IGF | 02/01/2025 | 31/12/2025 | 1,500.00 | - | Completed (100%) |  | A total of 328 (255 Males, females 73) farmers benefitted from the initiative. |
| Rearing for Food and Jobs (RFJ) | Economic Development | 300.00 | IGF | 02/04/2025 | 31/12/2025 | 300.00 | - | Completed (100%) |  | 10 poultry farmers(Males 6, females 4) were supported |
| Livelihood Empowerment Against Poverty (LEAP) | Social Development | 109,500.00 | IGF Donor | 02/01/2025 | 31/12/2025 | 22,500.00 | - | Completed (100%) |  | Cash grant was paid to 75 LEAP Beneficiaries (representing 20%. The remaining 80% however could access their grant because of technical challenges in the inter-bank payment system. |
| Integrated Social Services (ISS) Programme | Social Development | 35,000.00.00 | Donor | 02//01/2025 | 31/12/2025 | 35,000.00 | - | Completed (100%) |  | Not all school were covered because of insufficient funds |
| Green Ghana Programme | Environment, Infrastructure and Human Settlements | 98,000.00 | IGF | 10/06/2025 | 31/12/25 | 6,000.00 | 92,000.00 | Completed (100%) |  | 2025 Tree Planting is Completed but Monitoring is Ongoing |
| Capitation Grant | Social Development | 38,375,100.00 | GoG | 02/01/2024 | 31/12/2025 | 19,187,550.00 | 19,187,550.00 | Completed (100%) |  | Delay in release of the capitation affects running of the schools |

Source: LaNMMA MPCU, 2025

Analysis of Programme Register

A glance at the Programme Register outlines the 6No. Non-physical flagship programmes implemented by the Assembly for the year under review. All 6 were implemented but delay in release of statutory grants affected full roll-out of the programmes although the overall achievement was quite remarkable

Success Factors

The success factors for the modest achievement made were as follows:

- Timely release of funds by donor funds and to some extent IGF for the roll-out of the planned activities under the ISS Programme and among others.

- Supply of relevant inputs and financial resources for the Green Ghana Programme by the Forestry Commission and the Assembly

Failure Factors

The major setback for the full implementation of software programmes were:

- Delay in release of required funds statutory funds for smooth implementation of activities on schedule.

- Seeming disconnect between policy formulators and implementers.

- Absence of regular review process to ascertain policy implementation status for remedial action.

Extent of Successes and Failures in Relation to Goals and Objective Set by the Assembly

Although there were genuine challenges during the year, the overall impact of those shortcomings could not derail the attainment of the goals and objectives assigned for the period.

## 2.2 UPDATE ON DISBURSEMENT FROM FUNDING SOURCES (GH¢)

Annex 5:  Update on Revenue Sources: January – December, 2025.

| Revenue Sources | Estimates |  |  |  |  | Performance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2021 | 2022 | 2023 | 2024 Actual | 2025 Target | 2025 Actual |
| DACF | 4,539,752.00 | 3,985,401.52 | 3,985,401.52 |  | 40,619,638.12 | 735,896.43 | 1,587,161.28 | 1,050,492.70 | 1,411,384.13 | 40,619,638.12 | 20,900,161.21 |
| DACF- RFG | 1,521,044.00 | 1,641,044.00 | 2,696,767.65 | 4,885,400.00 | 1,561,965.00 | 1,121,044.00 | 1,144,509.65 | 76,414.25 | 1,785,763.00 | 1,561,965.00 | - |
| MP’s CF | 800,000.00 | 800,000.00 | 800,000.00 | 200,000.00 | 800,000.00 | 294,652.07 | 460,777.15 | 301,475.49 | 649,214.41 | 800,000.00 | 1,079,954.02 |
| IGF | 6,851,415.00 | 7,400,644.50 | 9,582,750.00 | 14,342,259.00 | 14,991,909.00 | 6,327,676.78 | 7,438,824.84 | 11,243,733.31 | 14,097,571.58 | 14,991,909.00 | 14,071,899.52 |
| MSHAP/HIV | 40,000.00 | 30,000.00 | 30,000.00 | 30,000.00 | 30,000.00 | 2,136.18 | 17,267.46 | 9,256.80 | 6,942.60 | 30,000.00 | 68,617.26 |
| PWDs CF | 250,000 | 200,000.00 | 200,000.00 | 200,000.00 | 200,000.00 | 70,101.69 | 149,104.21 | 116,638.74 | 169,954.16 | 200,000.00 | 200,875.73 |
| GSCSP | - | - | - | - | - | - | - | - | - | - | - |
| SRWSP | - | - | - | - | - | - | - | - | - | - | - |
| GSOP | - | - | - | - | - | - | - | - | - | - | - |
| UNICEF | - | 50,000.00 | 50,000.00 | 50,000.00 | 50,000.00 | 60,000.00 | 25,000.00 | 50,000.00 | 50,000.00 | 50,000.00 | 27,625.00 |
| LEAP | 35,000.00 | - | - | 72,000.00 | - | - | - | - | - | - | - |
| MAG/CIDA | 84,702.00 | 49,623.00 | 210,000.00 | - | - | 71,010.60 | 49,622.93 | 32,294.33 | - | - | - |
| GAMA | 50,000.00 | 50,000.00 | 50,000.00 | 50,000.00 | - | - | - | - | - | - | - |
| MP SIPF | 240,000.00 | 200,000.00 | 200,000.00 | - | 200,000.00 | - | 60,000.00 | 60,000.00 | - | 200,000.00 | - |
| GARID O&M GRANT/FUNDS | - | 220,400.00 | 420,971.00 | 705,531.40 | 705,531.40 | - | 220,400.00 | 420,971.00 | 502,587.33 | 705,531.40 | - |
| DECENTRALIZED DEPARTMENTS (GoG SUPPORT) | - | 141,944.00 | 89,000.00 | 49,000.00 | 150,000.00 | - | 43,629.23 | 48,377.01 | - | 150,000.00 | 46,389.89 |
| TOTAL |  |  | 18,314,890.17 | ..... | 59,309,043.52 | - |  | 13,409,653.63 | 18,673,417.71 | 59,309,043.52 | 36,395,522.63 |

Source: LaNMMA’s Finance Department, 2025

Analysis of the Performance of Funding Sources

As part of the Assembly’s Budget for 2025, it was projected that an amount of GHC 59,309,043.52 (compensation inclusive) was to be mobilized from 10 revenue sources. As of 31st December, 2025 a total revenue of GHC 36,395,522.63 representing 61.36% was mobilized from the 10 revenue streams. The highest revenue of GHC 20,900,161.21 was from the DACF. This was followed by an IGF of 14,071,899.52. Whereas some of the revenue sources received the total amount budgeted; others like GARID grant was not released. This variations to some extent affected planned activity implementation and thus necessitating mid-year review of some Departmental Workplans and Budgets as well as the overall 2025 Composite Annual Action Plan and Budget. The cumulative performance was remarkable notwithstanding the challenges encountered. Although micro analysis of some of the broad revenue streams relative to IGF reveal a decline for instance property rates collection attributable to contract termination issues.

Success Factors

A myriad of factors necessitated the successes chalked in the revenue mobilization efforts:

- Effective implementation of the Assembly’s RIAP and the associated strategies leading to astronomical performance in IGF which happened to be one of the best in the Greater Accra Region.

- The increment in the DACF grant transfer.

- Improved social services delivery also provided sufficient justification for rate-payers to honour bills served especially the business operators.

- Provision of additional vehicles in the previous years for revenue collection, re-constitution of Development Control Teams and Revenue Collectors, institutionalisation of reward and sanction regime for Revenue Collectors.

Factors for Failure

- Delay on the part of central Government and the full DACF allocation of 40,619,638.12

- Central Government Policy change in Property Rate Collection.

- Internally Generated Revenue collection and management challenges.

Extent of Achievements and Failures and their Connection to Goals and Objectives Set

The outstanding revenue or funding performance were not without hitches, however the implementation bottlenecks did not derail the realization of the goals and objectives set to improve the well-being of the good people of the Municipality.

### 2.2.1 UPDATE ON DISBURSEMENT

Annex 6a:  Update on Expenditure

| Budget Items | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure | Apprd. | Rlsd. | Exp. |
| Compen-sation | 8,027,284.13 | 7,944,668.51 | 7,944,668.51 | 7,482,006.85 | 7,984,603.19 | 7,984,603.19 | 9,204,169.56 | 10,567,757.50 | 10,567,757.50 | 14,637,362.56 | 14,808,964.12 | 14,808,964.12 | 16,705,511.00 | 17,395,883.91 | 17,395,883.91 |
| Goods and Services | 7,539,913.83 | 4,955,958.00 | 4,955,958.00 | 7,536,673.64 | 6,681,636.74 | 6,681,636.74 | 9,118,085.30 | 837,797.00 | 837,797. 00 | 13,888,291.50 | 9,578,880. 51 | 9,578,880. 51 | 11,547,060.72 | 22,027,537.00 | 6,305,336. 64 |
| CAPEX | 5,789,733.36 | 1,722,184.34 | 1,722,184.34 | - | 2,245,112.39 | 2,245,112.39 | 7,917,824.63 | 1,788,459.82 | 1,788,459. 82 | 8,352,208.45 | 1,772,099. 21 | 1,772,099. 21 | 32,770,073.81 | 4,297,400.91 | 4,297,400 .00 |
| Total | 21,356,931.30 | 14,622,810.80 | 14,622.80 | 15,018,680.50 | 16,911,352.30 | 16,911,352.30 | 26,240,079.50 | 13,194,014.30 | 13,194,014.30 | 36,877,862.51 | 26,159,943.84 | 26,159,943.84 | 61,022,645.52 | 43,720,821.82 | 27,998,620.55 |

Source: LaNMMA’s Finance Department, 2025

Analysis on Expenditure

It is worth mentioning that the Assembly estimated to mobilize a total revenue of GHC 59,309,043.52 which is inclusive of the projected staff compensation. At the end of 2025, GHC 36,395,522.63 was realized.

Success Factors

The key success factors that helped to keep expenditure within the budget limit include:

- Compliance to the Public Financial Management Act and the subsidiary legislations.

- Strict adherence to Budget Implementation Guidelines and its insistence on the operation of balanced budget.

- Enforcement of internal expenditure control systems.

Factors for Failures

There were only two key challenges with the expenditure bit of the revenue.

- Difficulty in accessing data from some Departments and Units of the Assembly for data consolidation and reporting.

- Rising recurrent expenditure especially on waste management thereby affecting budget for capital projects.

Impact of Successes /Failures on Goals and Objectives

To a very large extent, the successes made in respect of the expenditures for 2025 were enough to ensure the achievement of goals and objectives set for the period.

### 2.2.2 ASSEMBLY’S CAPEX BUDGET PERFORMANCE ANALYSIS

Annex 6b: MMDAs (Assembly’s) CAPEX Budget Performance Analysis

| Estimate |  | Release | Expenditure | Variance |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Unconstrained (A) | Constrained (B) | C | (D) | (A-B) | (B-C) | C-D |
| GOG | 21,993,511.41 | 22,323,623.11 | 21,993,511.41 | 22,323,623.11 | -330,111.70 | 330,111.70 |
| IGF | 920,009.48 | 14,071,899.52 | 14,071,899.52 | 14,071,899.52 | -13,151,890.04 | 0 |
| Donor | - | - | - | - | - | - |
| Total | 22,913,520.89 | 36,395,522.63 | 23,401,410.93 | 36,395,522.63 | -13,482,001.74 | 330,111.70 |

Source: LaNMMA’s Finance Department, 2025

Assembly’s CAPEX Budget Performance Analysis

The Assembly’s total Unconstrained Budget for 2025 was GHC 36,395,522.63 whereas the Constrained Budget for the same period was GHC 22,913,520. 89 .Actual release for 2025 was (GHC 36,395,522.63 with a corresponding expenditure of (GHC 23, 401, 410.93. This provides a variance of GHC 330, 111.70. Summary of the analysis evidently reveals a capital expenditure shortfall. This partly explains the inability of the Assembly to complete all capital projects implemented over the period.

Success Factors

The key success factors for Capex performance include:

- Assembly’s remarkable IGF and other revenue performance including donor grants

- Strict adherence to Budget Implementation Guidelines and its insistence on the operation of balanced budget.

Factors for Failures

The major failure factors were as follows:

- The inability of the Assembly to fully mobilise the projected revenue for the year (ie. from all revenue sources).

- The under-performance of some contractors which affected the project completions timelines for the period.

- The lack of control in the release of grants from both Central Government and Development Partners.

Impact of Successes /Failures on Goals and Objectives

Despite the inability of the Assembly to fully achieve its capex target for the year, the goals and objectives set for the period were partly fulfilled. The envisaged that all backlog of capital projects would cleared in 2025 and that lessons learnt would provide useful guidance for the Assembly’s future planning and project implementation strategies.

### 2.2.3 CAPEX BUDGET ALLOCATIONS AND IMPLEMENTATION FOR ACTIVE PROJECTS

Annex 6c: CAPEX Budget Allocation and Implementation for Active Projects

| Multi-Year CAPEX Throw Forward |  |  | MTBF Envelope |  | Performance |  |  |  | Details on Capital Projects, 2025 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total Medium-Term Plan Estimate ( plan) | Annual Estimate (plan) | Annual Estimate (plan) | Annual ceilings |  | Approved/Released | Expenditure |  |  |  |  | Project |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Code | Name | Age | Original Estimate cost |  | Revised cost | Expenditure to date | Outstanding Balance | Completion status |  | Time overruns | Cost Overruns | Land acquisition and resettlement |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | % | Picture |  |  |  |
| 2022-2025 | 2025 | 2024 | 2025 | 2024 | 2024 | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 27,468,294.80 | 26,780,048.90 | 25,419,752.00 | 26,780,048.90 |  | 25,419,752.00 26,240,079.49 | - | 001 | Construction of 1No. 3-Storey 18-unit Classroom block with Ancillary Facilities for Pantang Hospital Basic School (Phase 1: Construction of 1No. 6-Unit Classroom Block) | 2 Months | 2,379,224.00 |  | - |  |  | 45% |  |  | - | Land was legally acquired by the Assembly and Ghana Education Service from Pantang Hospital Authorities |
|  |  |  |  |  |  | - | - | Construction of 2No. 18-Unit 3-Storey Retail Shop and 2No. 24-Unit Market Shed at Madina Market (Phase 2) | 18 Months | 13,501,251.94 |  | - | 12,953,321.94 | 547,930.00 | 75% |  |  |  | The land was legally acquired by the Assembly through the Bethlehem Congregation of Presbyterian Church of Ghana |
|  |  |  |  |  |  | 456,304.25 | - | Construction of 1 No. 5-Unit KG Block with Ancillary Facilities for Fire Armour Basic School | 28 Months | 549,200.00 |  | - | 250,000.00 | 299,200.00 | 100% |  |  |  | Land was legally acquired by the Assembly and the Ghana Education Service |
|  |  |  |  |  |  | 108.510.00 | - | Procurement and Distribution of Assorted School Furniture to Selected 1st and 2nd Cycle Schools | - | - |  | - | - | - | 70% |  |  |  | - |
|  |  |  |  |  |  | - | - | Construction of 1No. 3-Storey Office Accommodation with Conference Hall and Ancillary Facilities for Oyarifa Zonal Council (Phase 1) |  | 2,402,577.70 |  | - | - | - | 25% |  |  |  | Land was legally acquired by the Assembly through Bethlehem Congregation of Presbyterian Church of Ghana. |
|  |  |  |  |  |  | - |  | Installation of 500m Length of Wire Mesh Protection Fence Along Madina Zongo Junction Stretch of the N4 Road | 3 Months | 548,637.50 |  | - | 400,000.00 | 148,637.50 | 80% |  |  |  | - |
|  |  |  |  |  |  | - | - | Gravelling and Spot Improvement of Selected Road in the Municipality | 7 Months | 840,159.20 |  | - | 526,968.80 | 313,190.40 | 100% |  |  |  | - |
|  |  |  |  |  |  | - |  | Construction of 1.2M Pipe Culvert at Sakora West Adenta | 7 Months | 154,795.00 |  | - | 127,181.25 | 27,613.75 | 100% |  |  |  | - |
|  |  |  |  |  |  | - |  | Desilting of Drains and Culverts at Raidul Jannah Mosque | 12 Months | 25,580.00 |  | - | 25,378.00 | 202.00 | 100% |  |  |  | - |

Source: LaNMMA Finance Department, 2025

Analysis of the CAPEX Budget Allocation and Implementation for Active Projects

A number of capital projects were earmarked for implementation in the Assembly’s MTDP 2022-2025. These projects were also prioritized and captured in the yearly annual action plans of the Assembly. The CAPEX Budget allocation is hereby analyzed vis-a-vis the implementation status. A total of 9 capital projects were implemented directly by the Assembly and other Central Government Agencies. For those rolled out by the Assembly, all relevant financial details are spelt out. All attempts by the Assembly to obtain those details for records and reporting purposes were unsuccessful. Generally, significant progress were on all of them. That notwithstanding, some financial commitments are yet to be honoured by the project awarding institutions including the Assembly. The various contractors also have obligations to discharge. It is expected that the awarding institutions (including the Assembly) would expedite action on outstanding payments since all projects are completed

Success Factors

Success factors were as follows:

- The improved revenue performance resulting from IGF growth and grant support allocations.

- Renewed commitment from contractors following payments received from awarding authorities.

Factors for Failure

Key challenges that bedeviled the total achievements of target for the year were:

- Irregular payment of contractors by awarding institutions

- Sheer backlog of roll-over projects with time overruns

Impact of Successes and Failures on the Achievement of Set Goals and Objectives

There has been teething challenges over the period, but the overall analysis of successes chalked in relation to challenges gives an indication of the realization of goals and objectives set. All completed projects must however be put to use whilst rolled over projects are given priority for early completion.

### 2.2.4 CUMULATIVE CAPEX THROW FORWARD AND MTBF ENVELOPE 2025-2027

Annex 6d: Cumulative CAPEX Throw Forward and MTBF Envelope, 2025-2027

| Items | Amount (GHC) |
| --- | --- |
| CAPEX Throw Forward | 5,316,297.63 |
| MTBF (Ceilings) | 5,500,000.00 |
| Variation | 183,702.37 |

Annex 6d highlights the cumulative CAPEX Throw Forward for the next 3 years which GHC 5,316,297.63 with a Ceiling of GHC 5,500,000.00. A variation of GHC 183,702.37 however exists for consideration over the period under reference.

### 2.2.5 AMOUNT OF CAPITAL ENVELOPE SPENT ON ACTIVE PROJECTS

Annex 6e: Amount of Capital Envelope Spent on Active Projects

| Sector | Capital Envelope Amount | Amount Spent on Rollover Projects | Amount Spent on New Projects |
| --- | --- | --- | --- |
| Education | 2,399,059.00 | 659,359.00 | 1,739,700.00 |
| Health | 512,640.00 | 512,640.00 | - |
| Water | 234,401.00 | - | 234,401.00 |
| Security | 1,559,636.00 | - | 1,559,636.00 |
| Road | 746,518.34 | 197,528.98 | 548,989.36 |
| Sanitation | 579,403.00 | 152,962.00 | 426,441.00 |
| Total | 6,031,657.34 | 1,522,489.98 | 4,509,167.36 |

Source: LaNMMA Finance Department, 2025

In relation to Annex 6e, a cumulative total of GHC, 6,031,657.34 was earmarked to be spent on prioritized rollover as well as new capital projects. The total expenditure regarding the rollover projects was GHC 1,522,489.98 whilst that of new projects was GHC 4,509,167.36.

### 2.2.6 ESTIMATED COST AND COST OVERRUNS OF ACTIVE PROJECTS

Annex 6F:  Estimated Cost and Cost Overruns of Active Projects

| Sector | Total Contract Sum | Revised Contract Sum | Cost Overruns | Actual Payments | Outstanding Balance | % Work Done |
| --- | --- | --- | --- | --- | --- | --- |
| Education | 2,399,059.00 | - | - | 2,081,332.60 | 317,726.40 | 100% |
| Health | 512,640.00 | - | - | 507,001.77 | 563.23 | 100% |
| Water | 234,401.00 | - | - | 213,000.00 | 21401.00 | 100% |
| Security | 1,559,636.00 | - | - | 1,449,849.83 | 109,786.17 | 100% |
| Road | 746,518.34 | - | - | 657,019.72 | 89,498.62 | 100% |
| Sanitation | 579,403.00 | - | - | 557,688.00 | 21,715.00 | 100% |

Source: LaNMMA Finance Department, 2025

Annex 6f provides overview of estimated cost overruns for the active projects of the Assembly for the period 2025. Although outstanding pays exist, there is no notable cost overruns. It is worth noting that all projects under consideration are completed.

## 2.3 UPDATE ON INDICATORS AND TARGETS

Annex 3: Performance on District Indicators

|  | Indicator (Categorized by Development Dimension) | Baseline 2021 | Actual 2022 | Actual 2023 | Target 2024 | Actual 2024 | Target 2025 | Actual 2025 | Key Programmes Undertaken During the Year | Challenges Encountered in the Year | Departmental Policy Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dimension : Economic Development |  |  |  |  |  |  |  | - Register at least 200 farmers on the Planting for Food and Jobs Programme - Train 30 women on flesh Yoghurt Production - Conduct yield studies for five selected crops (Maize, Pepper, Okro, Cassava & Tomatoes) within the Municipality - Promote the production and distribution of 1,000 cockerels to improve the nutritional status and incomes of households - Undertake at least 480 home and farm visits quarterly to extend agricultural technologies to farmers and follow-up on trainings - Conduct Monitoring and Evaluation of planned activities in collaboration with the Municipal Planning Coordinating Unit (MPCU) of the Assembly - Organize one District Agricultural Planning Session with farmers and other stakeholders (RELC) by Dec. 2024 - Conduct active surveillance of diseases in poultry and livestock - Train 10 farmer group executives on marketing strategies and link them to markets - Set up one aquaculture demonstration and train 20 potential fish farmers on small scale fish farming Etc. | - Inadequate funds and delays in funds releases - Lack of Veterinary Clinic - Inadequate infrastructure such as roads, irrigation systems and storage facilities - Inability of the Department to provide pesticides for FAW Control - The non-celebration of the 2024 Farmers Day created agitations among some farmers | - Increase resource allocation and timely release of funds - Government should prioritize investment in infrastructure including roads, irrigation systems, storage facilities |
| 1. | Total output in agricultural production Maize Pepper Tomato Cassava Okro Cattle Sheep Goat Pig Poultry | 153.51 38.77 30.02 18.49 1,224 124.61 1,161 2,493 468 59,796 | 170.57 43.08 33.35 138.45 22.87 1,496 1,290 2,773 520 66,440 | 193.83 48.41 37.26 22.87 1,414 160.06 1,445 2,992 551 76,738 | 193.75 39.23 48.40 160.00 22.72 1,490 1,500 3,050 620 77,000 | 203.14 52.24 39.23 171.21 24.33 1,473 1,421 3,027 592 77305 | 210.00 55.00 40.00 175.00 25.00 1,500 1,600 3,200 450 78,000 | 198.20 56.13 42.56 175.50 26.37 1,582 1,696 3,326 473 78,927 |  |  |  |
| 2. | Average Productivity of Selected Crops (mt/ha) | 38.77 | 43.08 | 48.41 | 90 | 98.03 | 98.03 | 99.75 |  |  |  |
| 3. | Percentage of Arable Land Under Cultivation (ha) | 30 | 23 | 19 | 21 | 24 | 24 | 23.89 |  |  |  |
| 4. | Number of New Industries Established - Agriculture - Industry - Service | 0 0 2 | 0 1 1 | 5 1 21 | 10 10 0 | 8 8 0 | 7 0 0 | 5 0 0 |  |  |  |
| 5. | Number of New Jobs Created iv. Agriculture v. Industry vi. Service | 0 0 50 | 10 200 0 | 5 8 21 | 10 3 0 | 8 5 0 | 7 0 0 | 5 0 0 |  |  |  |
| 6 | Percentage change in IGF | 7.5% | 8.16% | 51% | 20% | 10.42% | 4.53% | 0.18% (Decrease) | - Conduct regular monitoring of revenue collection and lodgement - Undertake unannounced spot checks on revenue collectors | - Persistent attempt by revenue collectors to introduce fake receipts and under-declare revenue collected | - That stiffer punitive measures be taken against revenue collectors found culpable. |
|  | Dimension : Social Development |  |  |  |  |  |  |  |  |  |  |
| 7 | Net Enrolment Ratio iii. Kindergarten iv. Primary v. JHS | 98.5 98 102 | 102 101 112 | 101 102.9 120.3 | 100% 100% 100% | 81.2% 87.2% 89.6% | 100% 100% 100% | 83.1% 81.0% 89.3% | - Sustained public education and counselling of parents/guardians on the need to send their children to school. - Explanation of Government policies on education | - Inadequacy of basic teaching and learning materials and equipment like computers, furniture etc. | - That Government must provide additional teaching and learning materials and equipment in schools |
| 8 | Gender Parity Index i. Kindergarten ii. Primary iii. JHS iv. SHS | 0.5 1 1.02 0.4 | 0.9 1.3 1.5 0.3 | 1.0 1.09 1.08 1.0 | 1.0 1.0 1.0 1.0 | 1.0 1.0 1.9 0.3 | 1.0 1.0 1.0 1.0 | 1.0 1.0 1.9 0.2 |  |  |  |
| 9 | Completion Rate I Kindergarten ii. Primary iii. JHS iv. SHS | 98% 170% 91% 72% | 140.7% 110.5% 117.2% 19% | 142% 111.5% 118% 24% | 100% 100% 100% 40% | 118.6% 198.2% 148.9% 36% | 100% 100% 100% 40% | 117.6% 197.2% 148.6% 36% |  |  |  |
| 10 | Pass Rate - JHS - SHS | 100% 100% | 99% 100% | 97.5% 100% | 100% 100% | 94.56 88.24 | 100% 100% | 96.50% 82.12% |  |  |  |
| 11 | Proportion of Health Facilities that are Functional i. CHPS Compound ii. Clinic iii. Health Centre iv. Polyclinic v .Hospital | 1 - 1 2 1 | 1 - 1 2 1 | 100% N/A 100% 100% - | 100% N/A 100% 100% - | 100% N/A 100% 100% - | 100% N/A 100% 100% - | 1 26 2 3 12 | - Construction of additional modern Health facilities - Speeding up the completion of health facilities under construction - Routine maintenance of existing health facilities | - Poor state of infrastructure and equipment - Inadequate space at the facilities - Insufficient specialists or personnel in specialised fields - Increasing service delivery pressure | - That Government should provide additional health facilities to cope with service pressure |
| 12 | Prevalence of Mal-nutrition (Institutional) - Wasting - Under Weight - Stunting - Over Weight | 0 0 0 0 | 0 0 2.3 0 | 0 0 1.5 0 | 1:38 1:21 1.0 99 | 1:47 1:23 0.5 114 | N/A 1500 150 99 | N/A 1,405 188 43 | - Public sensitisation - Community outreach programmes - OPD attendance and record taking - Nutritional promotion talks - Promotion of maternal health services - Sustained anti-malaria campaign - Sustained enforcement of COVID-19 Protocol eg wearing of nose masks and handwashing with soap - Public sensitisation on the importance of NHIS - Community level registration - Special registration of indigents and the vulnerable | - Inadequate logistics and support for outreach programmes eg. vehicles and fuel - Poor data collection and management practice - Irregular antenatal attendance - - Inadequate logistics for fieldwork - Apathy on the part of the public | - That Government with the support of all relevant stakeholders must provide the necessary logistical and technical support to address existing challenges. - That education on maternal health must be intensified - That the protocol enforcement must not completely be suspended - Government must address the operational challenges of the NHIS to improve public confidence and acceptability |
| 13 | Maternal Mortality Ratio (Institutional) | 0 | 9.3 | 129.1 | 127.77 | 240.73 | 0 | 560.13 |  |  |  |
| 14 | Malaria Case Fatality (Institutional) i. District ii Under Five iii. Women between 15-49 | 0.0 0.0 0.0 | 0.0 0.0 0.0 | 0.0 0.0 0.0 | 0 0 0 | 0 0 0 | 0 0 0 | 2 2 0 |  |  |  |
| 15 | Proportion of Population Who Have Tested Positive for COVID-19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |
| 16 | Proportion of Population with Valid NHIS Card i. Total ii. Indigents iii. Informal iv,Aged v.Under 18 Years vi. Pregnant Women | 40% Males: 18% Females: 22% | 48% Males: 20% Females: 28% | 36.4% Males: 30.5 Females: 42.1% | 55% | 45.0% Males 39.0% 50.8% | 61.0% | 45.0% (Male 39%, Female 50.8%) |  |  |  |
| 17 | Number of Births and Deaths Registered i.Birth (Sex: ) ii.Death (Sex, Age Group) | B 6,820 273 | 7,490 212 | Births 12,544 (Male: 6,499 Female: 6,045) Deaths 198 (Male: 108 Female: 90) | Births 15,000 (Male: 8,000 Female: 7,000) Deaths 0 (Males: 0 Female: 0) | Births 18,521 (Male: 9,211 Female: 9,310) Deaths 208 (Males: 114 Female: 94) | T Births 15,000 (Male: 8,000 Female: 7,000) Deaths 0 (Males: 0 Female:0) | Births 8,139 (Males 4 447, Female 3692) Deaths 44 (Males 27, Female:17) | - Community registration outreaches - Public sensitisation on the importance of birth and death registration | - Poor public attitude towards registration | - Sustained public education to whip up public interest |
| 18 | Percentage of Population with Sustainable Access to Safe Drinking Water Sources i.District ii Urban iii. Rural | 97% 45% 52% | 98% 47% 51% | 98.2% 50% 48.2% | 100% 50% 48.2% | 99% 96% 42% | 100% 50% 48.2% | 96% 49% 48.8% | - Facilitation of potable water extension - Support for household toilet construction - Institutionalisation of clean-up exercises at the community level - Registration of households for waste collection | - Inadequate investment for expansion of existing system - Inability of households to pay for services - Apathy of community members towards clean-up exercise | - That Central Government must increase support for expansion of the network - That Government must consider re-introduction of subsidy on household toilet construction - Enforcement of sanitation bye-laws and regulations |
| 19 | Proportion of Population with Access to Improved Sanitation Services i.District ii Urban iii. Rural | 52% 22% 30% | 53% 24% 29% | 58% 28% 30% | 68.5% 69.2% 62.0% | 69.3% 70.0% 62.3% | 78.% 80% 78% | 77.23% 78.03% 71.30% |  |  |  |
| 20 | Recorded Cases of Child Abuse i.Child Trafficking ii Child Labour iii. Sexual Abuse iv. Emotional Abuse v.Neglect vi. Early Marriage vii. Female Genital Mutilation viii.Family-Child Separation | 0 0 3 3 14 0 0 15 | 0 0 10 30 65 0 0 24 | 0 0 0 2 11 0 0 2 | 0 0 0 0 0 0 0 2 | 0 0 0 70 111 0 0 0 | 0 0 0 0 0 0 0 0 | 0 0 193 0 0 0 0 193 | - Promotion of child rights - Advocacy for redress for survivors of violations | - Enforcement of relevant laws and regulations | - Intensification of human rights sensitisation |
| 21 | Percentage of Road Network in Good Condition i.Total ii. Urban iii. Feeder | 49% 7.5% 60% | 26% 6% 20% | 51.1% 8.1% 43% | 100% 100% 100% | 41% 34% 65% | T 100% 100% 100% | 96.5% 3.48% | - Grading and rehabilitation of selected roads | - Inadequate funding - Lack of regular maintenance | - Provision of adequate funding to improve road infrastructure |
| 22 | Percentage of Communities Covered by Electricity - District - Rural - Urban | 98% 98% 100% | 98.5% 98.02% 100% | 98.7% 98.3% 99.5 | 51.1% | 52% | 60% | 55% 98.% 98% | - Facilitation of electricity connection | - Delay in deployment of services especially acquisition of meters | - Streamlining and standardization of service procedures |
| 23 | Reported Cases of Crime - Rape - Armed Robbery - Defilement - Murder - Drug Trafficking - Peddling - Drug Abuse - Domestic Violence | 0 10 0 1 0 0 30 0 | 0 0 0 2 0 0 0 361 | 0 0 0 0 0 0 15 18 | 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 23 19 | 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 193 0 | - Public education on crime prevention - Enforcement and prosecution of offenders | - Operational/logistical constraints of the Ghana Police Service - Inadequate personnel | - Improvement of logistical support to enable the Police operate effectively to reduce crime incidence - The Police and other relevant agencies must collaborate step up public education to reduce domestic violence |
| 24 | Number of Communities Affected by Disaster - Bushfire - Domestic Fire - Industrial/Commercial Fire - Floods - Wind /Rain Storm | 0 2 1 5 | 0 4 1 8 0 | 0 2 1 12 1 | 0 0 0 0 0 | 0 8 2 14 0 | 0 0 0 0 0 | 0 4 2 5 0 | - Municipal-wide public sensitisation on disasters and mitigation strategies - Desilting of selected drains | - Inadequate funding to improve drainage and electrical infrastructure - Poor attitude towards disasters - Ineffective enforcement of laws and regulation | - That Central Government must support the Assembly to expand its drainage and electricity infrastructure - That building and environmental regulations must be strictly enforced by the Assembly and other agencies |
| 25 | Percentage of Annual Action Plan Implemented | 95.38% | 96% | 95.1% | 25% | 23% | 27 | 25 | - A total of 148 activities implemented out of the Annual Action Plan cut across all the development dimensions | - Inadequate funding for planned activities - Insufficient logistics for fieldwork | - That Management must intensify resource mobilisation to improve the implementation of planned programmes and projects |
| 1 | Number of Trainings Conducted on ISSOPs | 1 | nil | 1 | 1 | 1 | 1 | 1 | - Conduct of training to build capacity of stakeholders on ISSOPs - Conduct of sensitisations on child rights - Conduct of stakeholder sensitisation on Child Protection and SGBV - Registration of LEAP beneficiaries onto the NHIS - - Organisation of community outreach programmes - Care management support offered - Training of NGOs and RHCs - Re-unifying of foster children with their parents - Monitoring of RHC - Placing of children without standard foster care in foster homes - - | - Inadequate funding - Inadequate funding - Difficulty in accessing vehicles for fieldwork - - - - - - - - - - - - - - - - | - That Central Government and the Municipal Assembly must provide additional funding to augment the UNICEF grant - That Central Government and the Municipal Assembly must provide additional funding to augment the UNICEF grant - - - - - - Continuous capacity building programmes for NGOs and RHC operators - That foster care standards and guidelines must be strictly enforced - - |
| 2 | Proportion of case Workers Trained in Child Protection and Family Welfare | 10% (9F, 1M) | 10% (9F, 1M) | 10% (9F, 1M) | 25% | 25% |  | 3m 8f |  |  |  |
| 3 | Number of Child Violence Cases Benefitting from Social Welfare /Social Services | 2 | 1 (1F) | 3 (1F, 2M) | 1 | 1 | 5 | 2 |  |  |  |
| 4 | Number of Children Reached by Social Work/Social Services | 246 | 260 | 385 | 540 | 562 | 560 | 530 |  |  |  |
| 5 | Number of People Reached with Child Protection and SGBV Information | 5,231 | 4,133 | 4.725 | 2,950 | 3,857 | 4,500 | 4,192 |  |  |  |
| 6 | Number of LEAP Household Members on NHIS | 365 | 350 | 350 | 100 | 62 | 353 | 187 |  |  |  |
| 7 | Number of Households with Adolescent Girls Benefitting from LEAP | 39 | 39 | 39 | 40 | 42 | 42 | 40 |  |  |  |
| 8 | Number of Outreach Visits to Communities with LEAP Households | 6 | 6 | 6 | 1 | 1 | 10 | 7 |  |  |  |
| 9 | Number of Referrals Received from GHS | 20 | 23 | 30 | 50 | 57 | 55 | 54 |  |  |  |
| 10 | Proportion of Referrals Receiving Adequate Follow-ups | 20% | 23% | 30% | 60% | 60% | 65% | 65% |  |  |  |
| 11 | Number of DSWCD’s that Have Shared their MMDAs’ LEAP Household Data with both NHIS and GHS | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| 12 | Number of Regional Inter-sectoral Monitoring Visits Conducted | 1 | 1 | 1 | 0 | 0 | 1 | 1 |  |  |  |
| 13 | Number of Meetings Organised to Discuss Integrated Services | 4 | 4 | 5 | 1 | 1 | 1 | 1 |  |  |  |
| 14 | Number of Girls Reached by Prevention and Care Services | 1,500 | 1,783 | 1,117 | 1,450 | 1,611 | 2,500 | 2,452 |  |  |  |
| 15 | Number of CP/SGBV Cases Referred to Other Services and Followed up | 2 | 1 | 3 | 40 | 26 | 15 | 10 |  |  |  |
| 16 | Number of NGOs including RHCs Trained | 1 NGO, 2 RHC | 1 NGO, 2 RHC | 2 RHC | 3 | 3 | 3 | 4 |  |  |  |
| 17 | Number of Children in RHCs Profiled and Re-unified | 20 profiled | 20 profiled, 2 reunified | 18 profiled | 75/3 | 75/3 | 91/10 | 91/10 |  |  |  |
| 18 | Proportion of Sub-standard RHCs Closed | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |
| 19 | Number of Children Placed in Foster Care | 5 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |
| 20 | Proportion of Population with Access to Basic Drinking Water Sources | 97% | 98% | 98.2% | 100% | 96% |  |  |  |  |  |
| 21 | Proportion of Population with Access to Improved Sanitation Services | 52% | 53% | 58% | 68.5% | 69.3% |  |  |  |  |  |

Source: LaNMMA MPCU, 2025

Analysis of the Performance of the Prescribed Core District Indicators in Relation to Goals and Objectives in the MTDP of the Assembly

This analysis of the Municipality’s performance on the basis of the Core Development Indicators and in the context of the Assembly’s Goals and Objectives for the year as captured in Annex 3, provides useful insights into the various development interventions implemented by the Assembly in 2025. The results of the analysis provide basis for the planning and review of programmes and projects for the Assembly’s 2026 Annual Action Plan.

For ease of reference, the analyses have been segmented along the broad Development Dimensions of the Agenda for Jobs II namely: Economic Development, Social Development, Environment, Infrastructure and Human Settlements; Governance, Corruption and Public Accountability, Emergency Planning and COVID-19 Response as well as Implementation, Co-ordination, Monitoring and Evaluation.

### 2.3.1. Development Dimension: Economic Development

The Assembly’s performance in relation to the core development indicators under the Economic Development Dimension has been impressive in 2025. Production levels in the selected staple crops and livestock substantially experienced an increase. Production levels in selected staple crops (specifically maize, cassava, Pepper, Tomato and Okro) was 498.76 metric tonnes as against a cumulative target of 505. For the same period, the cumulative livestock and poultry production shot up to 86,004 metric tonnes as against a target of 84,750.00 for the year. The average productivity of selected crops at the end of 2025 stood at 99.75 metric tonnes compared to the annual target of 98.03.

The total hectares of farms cultivated (i.e. arable land cultivated) decreased slightly from 24 hectares in 2024 to 23.89 hectares in 2025. This is attributable to the loss of farmlands to real estate development.

Although the target set for new industries established in 2025 was not fully met, the number of new industries created were 5 (which were under Agriculture).  The Assembly’s internally generated revenue was GHC 14,071,899.52 as against a projected target of GHC 14,991,909.00. Despite the target not being met, it was significant performance against the background of property rate collection contract abrogation

Success Factors

A variety of factors account for the strides made with regard to the core District Indicators:

- Also, the improvement in IGF collection of 2025 being GHC 14,071,899.52 has been a remarkable achievement contributing to the economic gains made. This enhanced the roll-out of majority of planned economic activities.

Factors for Failure

- Government’s policy shift on property rate collection also affected the effective collection because third party collection contracts were terminated.

- The delay in release of 2025 DACF by Central Government affected implementation of Interventions tied to the funding source.

Successes /Failures and their Connections to Goals and Objectives Set by the Assembly

All in all, the successes recorded relative to the core indicators had a positive impact on the attainment of the overall goals and objectives of the Assembly for 2025. There was commensurate improvement in the lives of the people in the Municipality as far as service delivery is concerned, albeit there is room for improvement.

### 2.3.2 Development Dimension: Social Development

The performance of the Core District indicators regarding the Social Dimension activities implemented in the course of 2025 generally points to a positive trend. The enrolment performance in education at both, the KG, primary and JHS levels improved significantly. Although targets set in all the three levels were neither fully achieved nor exceeded: Kindergarten – 83.1% as against 100%, Primary – 81.0% as against 100% and JHS 89.3% as against 100%.

Gender Parity Index target for JHS in the year under review was exceeded (1.9 instead of 1.0).  The target for Primary and Kindergarten were achieved 1.0 and 1.0 respectively. However, performance for SHS was 1.0 instead of target 0.2.

Completion rate in all levels of schooling soared up except Senior High School which was 36% as against a projection of 40%. Kindergarten recorded 100% completion rate, the Primary Rate was 197.2% as, JHS chalked 148.6% as against the target of 100%.The BECE (JHS) Pass Rate for 2025 was 96.50% whilst that of WASSCE (SHS) stood at 82.12%. In both instances, there was a marginal drop in performance.

All existing health facilities in the Municipality were functional and patronized by general public. Underweight condition also decreased to 1,405. Stunting however declined.

Maternal mortality ratio was 560.13 per 100,000 births compared to 127.77 in 2024. Malaria fatality on the other hand was 2. By the end of 2025, 45% of the entire population of the Municipality had valid NHIS Cards. This has been a matter of concern to all well-meaning people within the Municipality and beyond. Massive enrolment drive is therefore being anticipated by the Municipal NHIA Office, the Health Directorate and Management of the Assembly in 2026 and beyond.

A total of 8,139 births (Males 4,447 and Females 3,692) were registered with 44 deaths (Males 27 and 17 Females) being recorded over the same period.

The percentage of population with access to drinking water was 96% as against a target of 100%. This stagnation in performance was due primarily to challenges with the Ghana water system and the Abokobi-Oyarifa-Small Town Water Supply System that serves more than a quarter of the Municipality’s population. Efforts are underway to fix the production and distribution challenges.

Population of the Municipality with access to improved sanitation over the period was, 77.23%.The rural and urban population access to sanitation in 2025 was 71.30 and 78.03% respectively.   A lot more progress are required in this sub-sector with clear-cut targeted interventions to bring it up to acceptable standard.

The total number of child abuse cases during the year was 193 as against 111 in 2024.The total percentage of roads in good condition was 96.5% compared to the 2024 annual percentage of 41%. Electricity coverage of the 22 communities in the Municipality was 55%.

The reported crime cases particularly in areas of drug and abuse  was 193, a development that had attracted grave public concerns because of the dire consequences for the future of the youth in the Municipality. Similarly, disaster cases reduced from 24 to 11 in the year under review.

The percentage of the Annual Action Plan implemented in relation to Medium-Term Development Plan was 23%.

On the District Specific Indicators regarding the Integrated Social Services (ISS) variables, the Assembly did not fair badly in the year under review. There were a total of 21 indicators. On the total number of training conducted for direct stakeholders of ISSOPs, the target of 1 training was met. In the vein, 11workers projected to undergo training in 2025were also trained.  The number of child violence cases that benefited from social services increased from 1 in 2024 to 2 in 2025. The total number of children reached with social services improved from also declined from 562 in 2024 to 530 in 2025.  The number of children sensitized on Child Protection and Sexual and Gender-based Violence shot up from 3,857 in 2024 to 4,192 in 2025. The number of LEAP Household Members on NHIS however reduced from 187 in 2024 to 62 in 2025. The number of Households with adolescent Girls that benefitted from LEAP were 42 as against the target of 40. During the year, there were 7 outreach visits to LEAP Communities with beneficiary households in 2025. A cumulative total of 54 referrals were received from Ghana Health Service as against a target of 55 for the year under review. The proportion of referrals that received follow-ups was 65%. The Assembly’s Department of Social Welfare and Community Development was able to transmit its LEAP Household data to National Health Insurance Authority and Ghana Health Service. There was 1 regional inter-sectoral monitoring was undertaken in the Municipality in 2025.However, 1 meeting was convened to discuss integrated social services. An impressive total of 2,452 girls were reached with prevention and care services in contrast to a target of 1,611 in 2024. The number of CP/SGBV cases referred for other services and follow-ups were 10 for 2025.  No sub-standard RHCs were closed down. No child was also placed in foster care.  The estimated number of 4 NGOs earmarked to be trained in 20245 were indeed trained during the year. The number of children in RHCs profiled and re-unified were 91/10. The proportion of population with access to potable water was 96% whereas that of sanitation hovered around 77.23%.

Success Factors for the Achievements

Success factors for the achievement made during the year are as follows:

- The successful implementation of Government’s educational policies such as the Ghana School Feeding Programme, Free Textbooks Distribution, Capitation Grant, Free Senior High School etc.

- Sustained public advocacy and education on the need for parents to send their children/wards to school.

- Persistent investment by the Assembly in the educational sector including construction of classroom blocks, provision of furniture, in service training as well as other teaching and learning materials.

- The UNICEF funding support for the implementation of the child protection activities largely enabled the Assembly to build institutional linkages, and also reduced child abuse cases.

- Effective inter-service and institutional collaboration provided a seamless service delivery for children in need of various social services during the year.

Factors for Failure

Among the factors that negatively affected the delivery of education and health delivery and the associated indicators were:

- Delay on the part of Government in honouring policy commitments to educational and health institutions.

- Inadequate health infrastructure and specialised services for instance the absence of Municipal Hospital and other referral facilities as well as gynaecologists and other health professionals.

- Inadequate funding and logistical constraints for instance: computers for schools, vehicles and fuel for supervision, monitoring and evaluation.

- Inadequate sanitation infrastructure and services

- Slow public response to attitudinal change sensitisation on sanitation management

- Poverty-induced child abuse and child right violations.

- The culture of silence in some communities leading to unreported or community –level settlement of child abuse cases also affected the realisation of some of the child vulnerability protection targets sets.

Successes /Failures and their Connections to Goals and Objectives Set by the Assembly

Though there were some failure factors, the successes attained far outweighed the failures. The successes chalked inured to the realization of the goals and objectives projected for 2025.

### 2.3.3 Development Dimension: Environment, Infrastructure and Human Settlements

Road infrastructure saw some relatively minimal improvement within the year. The percentage of road in good condition was 96.5% as against a target of 100%.. The electricity coverage target of 55% instead (60%).

Success Factors for the Achievements

A number of factors were responsible for the notable achievements made in respect of the above-mentioned Development Dimension:

- Delivery of the District Road Improvement Project (DRIP) equipment by Central Government helped to improve significant length road network in the Municipality although the equipment arrived late.

- The arrival of statutory funds and grants in the Assembly guaranteed some funding for the infrastructural projects.

Factors for Failure

Key challenges encountered include:

- Budgetary constraints thereby affecting electricity and road delivery targets.

- Delay in transfer of central government grants to the Assembly and how it affected planned activity roll-out.

Extent to Which Successes and Failures Affected Goals and Objectives Set

Though there were genuine challenges, the successes were sufficient to facilitate the realization of goals and objectives set in the Assembly’s MTDP.

### 2.3.4 Development Dimension: Governance, Corruption and Public Accountability

The Assembly made impressive progress as far as implementation of 2025 Annual Action Plan (AAP) is concerned. A significant number of planned Programmes and Projects for the year were implemented. However, the level of completion for some of the interventions was low. Service delivery for water, electricity, and health were relatively appreciable. However, sanitation services access ought to be improved drastically although the 2025 performance was a marked improvement over 2024. Engagements with the citizens in the planning, budgeting and programme and projects implementation generally were equally remarkable although successes chalked could be improved upon. Two Town Hall meetings and other popular participation platforms were created to plan, account to the citizenry and elicit feedback for improved service delivery and well-being.

Series of fora were also organized to educate the citizens on civic responsibilities, corruption and measures to eradicate it.

Success Factors

A number of factors made the achievements under this Development Dimension possible:

- Institutionalization of the popular participation policies of Government by the Assembly.

- Continuous public education on the importance of citizen participation in the governance process.

- Compliance to assessment requirements and performance contracts signed by the Municipal Chief Executive and the Co-ordinating Director respectively.

- Improved funding for related activities under the thematic area.

Factors for Failure

Factors that militated against the full realization of targets set were:

- Inadequate funding for the implementation of the Assembly’s popular participation strategies.

Extent to which Successes and Failures Affect the Achievement of Set Goals and Objectives

Although funding was a limiting factor, the successes made were sufficient for the achievement of set goals and objectives as outlined in the MTDP of the Assembly.

### 2.3.5 Development Dimension: Emergency Planning and COVID-19 Response.

Relative to the emergency planning and response activities, a number of disaster planning and sensitizations on bush, domestic and commercial/industrial fires, and disaster response activities were undertaken over the period. There was no specific COVID-19 activity. Eight domestic fires and 2 commercial/industrial fire were recorded as against the targets of zero (0). There was also one rain storm disaster and 14 flood disaster incidence as against a target of zero. Though the magnitude of devastation caused by theses disasters were minimal, the Assembly have deployed new strategies including massive public education, building of capacity for swift and effective response among others to avert recurrence of these disasters some of which are man-made thus preventable. Air pollution levels were also monitored throughout the year and relevant data were also shared with stakeholders to enable them take precautionary measures.

Success Factors

Success Factors for the modest achievements made under this Development Dimension include:

- Effective disaster response mechanisms that reduced the level of devastation caused by disasters during the year.

- Strong institutional collaboration that strengthened prevention and response capacity.

Factors for Failure

Factors that impeded the full realization of targets set were:

- Slow response to change of attitude towards refuse disposal and management.

- Inadequate enforcement of sanitation and spatial development bye-laws and regulations leading to haphazard development, crude dumping of refuse, blocking of waterways, encroachment on wetlands and greenbelts/buffers etc.

- Inadequate funding for drainage maintenance including regular desilting.

Extent of the Impact of Successes and Failures on the Achievement of Set Goals and Objectives

The failures recorded did not completely derail the Assembly’s efforts at realizing the goals and objectives outlined in the MTDP and for the year. It is however indisputable that the resolution of the failure factors could move the Assembly to higher pedestal as far as its emergency and disaster planning and management aspirations are concerned

### 2.3.6 Development Dimension: Implementation, Co-ordination, Monitoring and Evaluation

Co-ordination, monitoring and evaluation exercises were carried out as planned in 2025. Specifically, quarterly Monitoring and Evaluation (M&E) were undertaken on the Assembly’s programmes and projects implemented over the period with the collaboration of relevant stakeholders.

Success Factors

Major factors that facilitated the achievements made are as follows:

- Strengthened co-ordination, monitoring and evaluation of the Assembly’s Development Activities.

Factors for Failure

The only challenging factor that worked against the total achievement of this Development

Dimension was inadequate funding for the implementation of all planned programmes and projects.

Extent of Successes and Failures in Relation to Goals and Objectives Set by the Assembly

Inadequate funding was a major setback to the target set for the year as far as this Development Dimension is concerned yet it could not defeat the gains made. To a very large extent the successes chalked propelled the Assembly to the attainment of the goals and objectives set.

All in all, the Assembly’s, 2025 performance on the prescribed indicators on development covering the 6 Development Dimensions was inspiring even though there is room for improvement.

## 2.4 UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES FOR 2025

Annex 7a: Update on Critical Development and Poverty Issues for 2025

| Critical Development and Poverty Issues | Allocation (GHC) | Actual Receipt (GHC) | No. of Beneficiaries |  |
| --- | --- | --- | --- | --- |
|  |  |  | Target | Actual |
| Ghana School Feeding Programme (GSFP) | 77,500.00 | - | 15,500.00 | 15,092 |
| Capitation Grant | 65,000.00 | 63,958.50 | 14,500 | 14,213 |
| National Health Insurance Scheme (NHIS) | 5,750,000.00 | 5,590,650.00 | 115,000.00 | 111,813 |
| Support to Persons with Disabilities (PWDs) | 200,000.00 | 200,875.73 | 50 | 60 |
| Livelihood Empowerment Against Poverty (LEAP) | 1,752,000.00 | 75,920.00 | 365 | 73 |
| National Youth Employment Programme | 1,800,000.00 | 1,644,000.00 | 300 | - |
| One-District-One Factory Programme | 662,2000.00 | 5,3000,400.00 | 946 | 312 |
| One-Village- One Dam | - | - | - | - |
| Planting for Food and Jobs (PFJ) | 115,000.00 | - | 224 | - |
| Free Senior High School Programme | 36,307,814.40 | 30,401.00 | 7,500 | 7.450 |
| National Entrepreneurship and Innovation Plan | - | - | - | - |
| Others |  |  |  |  |
| Street Naming and Property Addressing Project | 122,760.00 | 2,000.00 | 50,000 | 48,432 |
| Persons with Disabilities (PWDs) | 120,000.00 | 116,638.74 | 320 | 305 |

Source: LaNMMA MPCU, 2025

Analysis of Critical Development and Poverty Issues/Interventions

A total of 12 critical development and pro-poor interventions were implemented by the Assembly in 2025 to mitigate poverty impact among approximately 241,372 constituents. Inadequate funding and weak policy implementation is affecting the full impact of the interventions.

Success Factors

- The only success factor is willingness on the residents to break out of extreme poverty by taking advantage of Government’s pro-poor programmes and policies

Factors of Failure

- In adequate funding and regular review of the interventions to make them more responsive.

Impact of Successes and Failures on Goals and Objectives Set in MTDP

- Notable successes were made but challenges out to be addressed as a matter of urgency to fully reap the impact of the interventions as well as goals and objectives set.

### 2.4.1 STAFF STRENGTH OF THE ASSEMBLY

Annex 7b: Staff Strength of La Nkwantanang-Madina Municipal Assembly (LaNMMA)

| Departments | Requirements |  | Actual | % Covered | Training Required |
| --- | --- | --- | --- | --- | --- |
|  | Minimum | Maximum | 2024 |  |  |
| Central Administration | 4 | 5 | 14 | 280% | - Contemporary Public Administration Practice |
| Executive Class | 4 | 4 | 10 | 250% | - Cotemporary Public Administration Practice |
| Procurement Unit | 2 | 3 | 5 | 166.6% | - Public Procurement Management |
| Management Information System(MIS) Unit | 5 | 6 | 3 | 50% | - Internet Management - Data Analysis - Infographic Designing |
| Development Planning | 3 | 5 | 5 | 100% | - Data Analysis - Project Management - Financial Proposal Writing - Public Administration and Management |
| Auxiliary Security Watchman Cleaner Records (Messenger) | 2 22 19 2 | 4 27 24 3 | 2 1 3 1 | 50% 3.7% 12.5% 33.33 | - Contemporary Security Management - Self-Defence Training - Training intelligence gathering - GIS and Remote Sensing Techniques |
| Internal Audit | 3 | 4 | 6 | 150% | - Modern Audit techniques - Public Financial Management |
| Budget Unit | 3 | 5 | 6 | 120% | - Public Financial Management |
| Agriculture | 3 | 5 | 16 | 320% | - Modern Farming Techniques, Crop and Animal Husbandry |
| Human Resource | 3 | 4 | 9 | 225% | - HR Management |
| Transport | 11 | 22 | 7 | 31.8 | - Defensive Driving and effective Vehicle Management |
| Environmental Health Unit | 19 | 34 | 34 | 100% | - Legal prosecution Skills |
| Social Welfare and Community Development | 3 | 5 | 26 | 520% | - Human Rights Promotion |
| Physical Planning | 3 | 6 | 6 | 100% | - Geographic Information System (GIS) |
| Births and Deaths | 3 | 5 | 7 | 140% | - Computer Skills and Data Analysis |
| Works | 4 | 6 | 12 | 200% | - Project Management - Public Procurement Management |
| Urban Roads | 1 | 2 | 4 | 200% | - Civil Engineering - Project Management - Quantity Surveying - Geographic Information System |
| Finance | 6 | 9 | 15 | 166.6% | - Public Financial Software Management - Monitoring and Evaluation |
| Statistics | 2 | 3 | 3 | 100% | - Data Collection, Analysis and Management, - Advanced ICT |

Source: LaNMMA Human Resource Department, 2025

Analysis of Staff Strength of the Assembly

The staffing situation in the Assembly is appreciable. Majority of the classes either have the required staff or over-staffed. However Departments such as the Transport, Management Information System Unit and the Auxiliary Staff Section of the Central Administration Department consisting of Junior Staff like Cleaners, security, Watchmen etc. are seriously under-staffed. The situation has overly increased the workload of staff in the above-mentioned Departments and Units respectively. This wide disparity between the workload of the staff under reference, and the remuneration available to them invariably culminates in persistent agitations from this category of staff. A development that calls for prompt remedial action. In contrast, there is relatively lesser work and productivity from majority of the Departments of the Assembly as depicted by the table above. Staff rationalization is recommended as an effective policy measure to ensure value for money.

Success Factors

Success factors include:

- Effective Human Resource Management System resulting in regular update and review of staff database has brought to the fore the lapses in the staffing situation.

Factors of Failure

Ineffective enforcement of staff rationalization policy and the staffing of the Local Government Service.

Impact of Successes and Failures on Goals and Objectives

The staffing imbalance however does not affect the achievement of the Assembly’s goals and objectives as set out in the MTDP. That notwithstanding, it is highly imperative for the Local Government Service to rationalize the staffing situation to enable the public sector optimize productivity.

### 2.4.2 CAPACITY DEVELOPMENT (Annex 7c: Capacity Development)

| Name or type of the Capacity Building | Venue/Location | Purpose of the Programme | Source of funding | Target group | Facilitators | No. of beneficiaries |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Total | Male | Female |
| One-Day Training on Procurement and Contract Processing | LaNMMA’s Assembly Hall | To Broaden Officers’ Knowledge on Procurement and Contract Issues | IGF | Procurement Officers and All Heads of Departments | GARCC and LaNMMA | 25 | 11 | 14 |
| One-Day Training in Records Management | LaNMMA’s Assembly Hall | To equip selected staff with the requisite skills in Records Management | IGF | Selected Staff | GARCC and LaNMMA | 15 | 4 | 11 |
| Training in Strategic HR Management | LANMMA’s Assembly Hall | To Enhance the Knowledge of staff in strategic HR Management to achieve the Assembly’s strategic goal | IGF | HR Managers and Assistant Directors | M/s Espeagles Consult | 13 | 2 | 11 |
| Training In Revenue Mobilisation | LANMMA’s Assembly Hall | To Improve the Revenue Base of the Assembly | IGF | Revenue Collectors | LaNMMA | 33 | 22 | 11 |
| Training In Case Management | LaNMMA’s Assembly Hall | To Improve Sanitation within the Municipality and equip Environmental Heath Officers (EHOs) with Knowledge and Sanitary Case Management | IGF | EHOs | M/s Espeagles Consult | 23 | 5 | 18 |

Source: LaNMMA Human Resource, 2025

Analysis of Capacity Development Requirements and Proposed Trainings

The generic and specific capacity requirements and proposed training/courses, as well as target staff, intended objectives and recommended training executing institutions have been analyzed. The analysis points to the necessity for some critical training courses to be provided to specific staff for optimum performance.

Success Factors

Effective staff appraisal system and capacity needs assessment for staff.

Factors of Failure

Low capacity of some staff and apathy towards training

Impact of Successes and Failures on Goals and Objectives

The varying staffing shortfalls and capacities did not significantly affect the realization of the Goals and Objectives se in the MTDP.

### 2.4.3 LOGISTICS ANALYSIS

7d: Logistics Analysis

| Required | Required | Actual | Remarks |
| --- | --- | --- | --- |
| Computers | 6 (3 Desktops, 3 Laptops) | 3 Laptops | 3No. Desktop with Accessories could not be procured in 2024. It has however been rolled over to 2025 |
| Printers | 3 | 2 | The procurement of 1No. Printer is outstanding. It is to be procured in 2025 to august existing stock for maximum output. |
| Projectors | 1 | 0 | The necessity for an additional projector remains relevant because of the obsolete nature of the existing one. |
| Office space | 6 | 2 | Additional office space is required to decongest some existing Departmental Offices |
| Vehicle | 7 | 5 | 3 Additional vehicles 2 Pick-ups and 1 Van is seriously required. |

LaNMMA Procurement Unit, 2025

Analysis of Critical Logistics and Working Tools of the Assembly

Given the sheer volume of work at the Assembly, coupled with the huge staff, logistics are of essence if the Assembly is to measure up to its mandate of effective service delivery.

Success Factors

Some key success factors include:

- Availability of some basic logistics and working tools

- Relative skill in the use and management of available logistics

- Effective enforcement of operation and maintenance plan

Factors of Failure

- Obsolete logistics and equipment and increasing cost of maintenance

- High cost of procuring logistics for effective managements of the Assembly and its Departments/Units.

Impact of Successes and Failures on Goals and Objectives

Although logistics deficit existed during the year, the successes recorded to a very large extent helped in the attainment of set Goal and objectives.

## 2.5 REPORT ON CRITICAL DEVELOPMENT AND POVERTY ISSUES

### 2.5.1 LIVELIHOOD EMPOWERMENT AGAINST POVERTY (LEAP)

The Livelihood Empowerment Against Poverty (LEAP) intervention is still running in the Municipality. There was no under payment of cash grants to LEAP Beneficiaries throughout 2025. The 98th cycle of payment was effected in 2025.However, only 20% of beneficiaries could access their payment. The remaining 80% of the beneficiaries whose Identification Cards were being renewed by the Ghana Inter-Bank Payment and Settlement System Limited could not be credited on time to enable them access their payment. The total of existing beneficiary households were 365. These comprised of 239 females and 126 males. A total of 138 NHIS cards of beneficiaries (made of 82 females and 56 males) were renewed during the year under review. No cards were however replaced. LEAP Reassessment Sensitization in Beneficiary Communities of the Municipality as well as Public Education and Sensitization on Ghana Pay Pilot Registration for Beneficiaries and District Level Engagement between Management of the Assembly and a team from LEAP Secretariat in Accra were also undertaken in the course of the year.

### 2.5.2 NATIONAL YOUTH EMPLOYMENT PROGRAMME BEING IMPLEMENTED THROUGH THE YOUTH EMPLOYMENT AGENCY (YEA)

The implementation of the National Youth Employment Programme in the Municipality continued in 2024. The programme’s main priority is to provide employment opportunities for the youth (initially between the ages of 15 to 35). The programme currently accepts persons above 35 years and offers a platform for skills training and development with opportunity for beneficiaries’ transition from short-term staff to permanent staff. During the year, the Assembly in collaboration with the Youth Employment Agency (YEA) and other relevant stakeholders sustained the implementation of three modules under the programme:  Community Police Assistants - CPA (Total 16: Males 4, Females 12), Artisanal Directory Module (Total 60:  Males 48, Females 12) Youth in Sanitation-YiS (Total 198: Males 90, females 108), Youth in School Support – YiSS (Total 9: Males 5, Females 4). Challenges confronting the implementation of YEA Modules in the Municipality in the year include inadequate office space and lack of funds for effective monitoring of the programme.

### 2.5.3 CAPITATION GRANT

Like all other Public Primary and Basic Schools, Schools in the Municipality are supposed to benefit from the Capitation Grant and Base support to Schools. In the 2024, a total of 14,213 students benefitted from the Capitation Grant (amounting to GHC 12,791,700.00) was released in support of the intervention. The amount per student in the year was increased to GHC 10.00 the previous year and the implementation was effected in 2024. Details of the beneficiary students at the various levels of the Basic School in the Municipality are as follows:  Kindergarten 1,402 (Males 708, Females 694), Primary 12,811 (Males 6,115, Females 6,696). Given the current inflation rate, it is expected that Government would review the rate further in line with the prevailing economic conditions of the country in order to achieve the true impact of the intervention.

### 2.5.4 FREE SENIOR HIGH SCHOOL PROGRAMME

The Free Senior High School (SHS) Programme has been one of the most crucial Flagship Programmes of Government of Ghana. Senior High School (SHS) students in the 2 Public SHS in the Municipality have benefited from the programme since its inception in 2017.  A total   of 8,874 students comprising of 5,800 males and 1,132 females benefited from the programme.  The intervention since its inception has significantly increased Senior Secondary School enrolment compared to the previous years. It is anticipated that stakeholders will continue to collaborate with Government to address emerging challenges in order to sustain the Free Senior High School policy. The online learning platforms introduced in the wake of the COVID-19 to enable students complete the WASSCE syllabi and sit their examinations is still in force. It is anticipated that the programme would be reviewed to shape up the implementation process.

### 2.5.5 SUPPORT TO PERSONS WITH DISABILITIES (PWDS) - PWDs COMMON FUND SUPPORT/UTILISATION)

Through the Persons with Disabilities’ (PWDs) component of the District Assemblies Common Fund (DACF), various support services are extended to PWDs in the Municipality. In line with the PWDs Guidelines, 80% of the Assembly’s share of PWDs Common Fund allocation is supposed to be applied in furtherance of economic empowerment of the beneficiaries. The remaining 20% is however supposed to be used to cater for medical expenses, school fees, accommodation rent and other school logistics as well as subsistence stipends. A total number of 318 PWDs (comprising of the Physically-Challenged Persons, Hearing-Impaired Persons, Visually-Impaired Persons and Persons with Albinism) have been registered by the Municipal Office of the Department of Social Welfare and Community Development (DSWCD).

In 2025, 60 PWDs benefitted from the PWDs Component of the District Assemblies Common Fund (DACF). These comprised of 37 males and 23 females. Economic Empowerment support and mobility items such as chest freezers, industrial sewing machines, water tanks, popcorn machines, oven, prosthesis were given to PWDs and to enhance their mobility. In addition, school fees and medical bills were also absorbed by the fund.

During the year in perspective, the Disability Fund Management Committee of the Assembly

held 2 quarterly meetings to deliberate on issues pertaining to the welfare of PWDS in the Municipality. Issues discussed included: Delay in in release of the DACF, NHIS Registration and Disbursement of funds to PWDs.

As part of planned activities for 2025, the Disability Fund Management Committee conducted a Municipal-wide monitoring of past beneficiaries of the Fund to ascertain the impact of the DACF on their livelihoods and the way forward. While some beneficiaries expressed gratitude to Government and the Assembly for the support, others called for incremental support to existing beneficiaries and expansion of the coverage of the support in order to rope in more PWDs.

On the whole, the initiative is making a positive impact on the beneficiaries. and that periodic review, coupled with the effective implementation of the monitoring and review findings will help scale-up the benefits of the intervention.

### 2.5.6 NATIONAL HEALTH INSURANCE SCHEME (NHIS)

The Municipality had a total National Health Insurance Scheme (NHIS) active membership of 111,813 (40,559 males, 57,084 females) which represents an increase of 1.09 % of the 2024 membership of 102,391 (40,257 males and 62,134 females). The total number of new registrants for the year 2025 was 14,170 (6,924 males, 7,246 females) which is a decrease of 80.63% of the 2024 total number of new registrants figure of 17,572 (males 8,481 and females 9,091) Total renewal of NHIS registration for 2025 stood at 97,643 (40,559 males, 57,084 females). The introduction of the Mobile Phone technology for renewal of registration in 2019 has tremendously helped to ease delays and frustrations that occasionally bedevil the membership renewal process. This technology is still in use and it is working effectively.

### 2.5.7 GHANA SCHOOL FEEDING PROGRAMME (GSFP)

The implementation of the Ghana School Feeding Programme (GSFP) which is intended to increase school enrolment, retention as well as improving the nutritional status of the pupils at the basic level through stimulation of local Agricultural production has been on course. The La Nkwantanang-Madina Municipal Assembly forty-two (42) schools benefitting from the GSFP in 2025, with a cumulative total of 13,058 learners/beneficiaries across the Municipality.  The GSFP implementation activities for the year consists of meetings, seminars, workshops and monitoring of implementation in the beneficiary schools within the La Nkwantanang-Municipality. The GSFP caterers are required to provide balanced diet according to the approved menu charts and are expected to remain consistent in meeting all contractual requirements. A minimum of four monitoring visits were undertaken by the Assembly’s School Monitoring Team to track implementation for possible improvement. Prevailing challenges in 2025 include: delay in payment of caterers, nutritional content balancing of food served, caterers’ inability to keep to food delivery and service schedules among others.

### 2.5.8 PLANTING FOR FOOD AND JOBS (PFJ) PROGRAMME

The Planting for Food and Jobs (PFJ) Programme has been an impressive stimulus to Agriculture production in the Municipality. In 2025, a total of 328 farmers (Males 255, Females 73) in the Municipality were registered under the Planting for Food and Jobs (PFJ).

### 2.5.9 YOUSTART GHANA JOBS AND SKILLS PROJECT

The Youstart Ghana Jobs and Skills project (a World Bank-supported initiative) was introduced by the Government of Ghana in May 2022 to fill the vacuum created by the phasing out of the Nation Builders Corp (NABCO) programme. A total of 358 (119 males and 239) females youth from the Municipality applied for the programme since inception in 2022. As of the end of 2025, One Hundred and Thirty-Eight (138) of the applicants progressed to the advanced stage of the grant disbursement successfully accessed the grant. The operations of these beneficiaries were closely monitored to ensure sustainability of the business started.

### 2.5.10 STREET NAMING AND PROPERTY ADDRESSING SYSTEM (SNPAS)

The Street Naming and Property Addressing Project implementation was pursued in 2025. Details of activities undertaken during the year are as follows: Digitization of 2,653 new street lines, Digitization of 15,226 Properties/Parcel and Mounting of 696 Signage. Challenges confronting the project include: inadequate logistics and untimely release of funds.

### 2.5.11 DISSEMINATION OF THE CO-ORDINATED PROGRAMME OF ECONOMIC AND SOCIAL DEVELOPMENT POLICIES (CPESDP) 2017-2024

To facilitate the dissemination of the official development policy document of the Government of Ghana (ie. Resetting Ghana Agenda), the La Nkwantanang-Madina Municipal Assembly following the national launch of the document initiated a number of strategies to disseminate the policy document to all relevant stakeholders. This was done through Stakeholder Fora, Town Hall Meeting Presentations and Official Speeches of the Assembly.

The objective has been to get stakeholders to appreciate the document in order to enlist their full support for the realization of the policies outlined for the development of the country. Four dissemination sessions targeting Assembly Members, Community Members, Civil Society Organisations (CSOs), Traditional authorities, Youth Groups, Women Groups and Persons with Disability were undertaken on Zonal Council Basis. A total of 380 stakeholders comprising of 210 males and 170 females were sensitized on the Resetting Agenda in the Municipality during the year.

### 2.5.12 IMPLEMENTATION OF THE NATIONAL ANTI-CORRUPTION ACTION PLAN (NACAP)

In consonance with Government’s policy of fighting corruption through the formulation, adoption and deployment of the National Anti-Corruption Action Plan (NACAP) to all public institutions, the La Nkwantanang-Madina Municipal Assembly developed a Municipal-specific Anti-Corruption Action Plan premised on the national one. All three activities outlined in the 2025 Annual Action Plan were fully rolled out by the Assembly. The Assembly through the implementation of its planned anti-corruption activities for the year was able to reach out to over 3,200 people. A sensitization forum on anti-corruption laws and regulations members of the public was carried out at Madina Zongo Junction while literature on anti-corruption (fact sheets, handbills etc.) were distributed to 2,500 community members.  The NACAP implementation process and periodic reviews will be sustained until the objectives of eradicating corruption are completely realized.

### 2.5.13 MUNICIPAL HIV AND AIDS RESPONSE

The Municipal response to HIV and AIDS as well as Tuberculosis was relatively remarkable in the 2025. A significant number of planned initiatives were effectively implemented to stem the transmission of HIV and also to manage existing HIV and AIDS-related infections. Two Municipal AIDS Committee (MAC) meetings were held to plan the roll-out of 2025 interventions on TB, HIV and AIDS.

A total of 3,763 students from 10 selected Schools in the Municipality were educated on Tuberculosis (TB), HIV and AIDS during 2nd and 3rd Quarters of 2025. Radio Advocacy talkshow was also organized to sensitize the public on the transmission and prevention of TB, HIV and AIDS. The Municipal HIV and AIDS Response Team undertook quarterly monitoring and evaluation of ART and PLHIV Centres across the Municipality. The team also distributed 2,600 condoms during the year in partnership with NGOs and philanthropists in addition to donating foodstuffs to Pantang OVCs.

The Ghana HIV and AIDS Network (GHANET) organized a 3-Day Training Workshop for Focal Persons on the Syndromic Management of Sexually Transmitted Infections (STIs) in Koforidua in which LaNMMA was a beneficiary. GHANET in partnership with GEC and LaNMMA organized a Health Walk as part of activities to mark the 2025 World AIDS Day Celebrations.

During the 2025 Independence Day Celebration, counselling and screening were conducted for100 persons on HIV and AIDS at the Madina Astro Turf Park.   The World Tuberculosis Day was also commemorated municipal-wide with public awareness creation in selected churches and mosque to advocate HIV and AIDS prevention, protection protocol and the use of PrEP and PEP.

On the whole implementation of planned activities were seamlessly carried out during the year.

### 2.5.14 IMPLEMENTATION OF 2024 GREATER ACCRA RESILIENT AND INTEGRATED DEVELOPMENT (GARID) PROJECT OPERATION AND MAINTENANCE WORKPLAN (DRAINAGE LOGISTICS PROCUREMENT, DRAINAGE CONDITION ASSESSMENT, DESILTING WORK ETC. UNDER THE GARID PROJECT.

The year 2025 was the final year for the implementation of the phase one of the GARID project in all 17 beneficiary Assemblies. Planned GARID activities regarding validation of drainage data collected in previous years were carried out. However, the final tranche of the GARID O&M Grant for flood, solid waste and climate change risks management interventions in the Odaw Basin was not transferred to enable the Assembly roll-out the planned activities for the period. External monitoring and audit teams from the project office in Accra undertook routine field work on the project in the Municipality during the year. The beneficiary Assemblies looks forward to the payment O&M Grant arrears and phase 2 of the project with improved focus on trans-boundary drainage infrastructure construction in the beneficiary Assemblies.

### 2.5.15 THE UNICEF-SUPPORTED INTEGRATED SOCIAL SERVICES (ISS) DELIVERY PROGRAMME

As part of measures to strengthen the delivery of integrated social services (ISS) to help address multi-dimensional poverty and vulnerability with a strong focus on promoting linkages between health, child protection, sexual and gender-based violence, UNICEF Ghana and the Government of Ghana. The ISS Programme which commenced in 2020 for 61 Assemblies ended in 2023 with a mutual agreement between the DPs and beneficiary Assemblies to sustain the programme beyond the donor funding phase.

Processes were initiated by the Department of Social Welfare and Community Development for funds to continue the implementation.  Funds were released for ISS activities were effectively applied in line with relevant guidelines.

## 2.6 EVALUATION AND PARTICIPATORY MONITORING AND EVALUATION

### 2.6.1 UPDATE ON EVALUATION CONDUCTED

Annex 8: Update on Evaluations Conducted

| Name of Evaluation Conducted | Policy/Programme/Project Involved | Consultant/Resource Persons Involved | Methodology | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Impact/Sustainability | Desilting of 1.82km Length of selected Drains in 2 Flood Hotspot Areas with LaNMMA (Pantang P&T Area and Madina UN Down/Chicago) | Municipal Planning Officer and Selected MPCU Members | Stakeholder Meetings & Field Visits | Drain Desilting and completed and are serving the intended purpose | That the negative impact of the seasonal flooding is largely alleviated but Routine Drain Maintenance Works and the construction of high capacity concrete Storm Drains would be relatively Lasting Solution to the Flooding Problems |
| Impact/Sustainability | Construction of 1 No. 3-Storey Accommodation for Kayaye | Municipal Planning Officer and Selected MPCU Members | Stakeholder Meetings & Field Visits | Facility is completed and in use | That the Facility is Serving the Intended Purpose but Periodic Maintenance Ought to be Undertaken on the Facility to Ensure a Longer Life span |
| Impact/Sustainability | Construction of 1 No CHPS Compound Block for Oyarifa Community | Municipal Planning Officer and Selected MPCU Members | Stakeholder Meetings & Field Visits | Facility is completed and in use | That the Facility is Serving the Intended Purpose but Periodic Maintenance Ought to be Undertaken on the Facility to Ensure a Longer Life span |
| Impact/Sustainability | Construction of 8 No. Institutional WC Toilets for Selected Schools | Municipal Planning Officer and Selected MPCU Members | Stakeholder Meetings & Field Visits | Facilities are completed and in use | That the Facility is Serving the Intended Purpose but Periodic Maintenance Ought to be Undertaken on the Facility to Ensure a Longer Life span |
| Impact/Sustainability | Grading Of 12km Length of Roads in Selected Communities (ie. Kweiman, Oyarifa Greenhill, Teiman Burger Town, Oyarfifa Tipper Junction Roads) of the Municipality. | Municipal Planning Officers and Selected MPCU Members | Stakeholder Meetings & Field Visits | Completed | That the Road Conditions have Improved but Periodic Maintenance Work and Sealing of the Road Would Provide Lasting Solution to Roads |

Source: LaNMMA MPCU, 2025

Annex 8 focuses on evaluation conducted, types of evaluation, methodology employed and stakeholders’ participation.  Evaluations were conducted on 5 completed projects to ascertain sustainability of their management and the impacts being derived by end users. The essence was to elicit feedback to inform future project design, implementation and management. In the final analysis the sustainability and impact of the projects handed over to the beneficiaries were quite impressive.

### 2.6.2 PARTICIPATORY MONITORING AND EVALUATION

Participatory monitoring and evaluation is a valuable tool/technique used to capture perceptions and assess whether the interventions in the DMTDP have met the expectations (objectives), especially, that of the poor and the vulnerable in the communities. The direct beneficiary community members were used in the monitoring and evaluation exercise.

The approaches used in the gathering of data for the 2025 Annual Progress Report included:

- Stakeholder Meetings (With the Use of Community Score Cards)

- Field Visits

- Focus Group Discussions

- Interviews

The results of the participatory monitoring and evaluation were very effective in addressing the needs of the people. The interface meeting with community members and service providers brought to the fore the need for service providers to improve delivery of essential services.

To ensure the effectiveness of the PM&E, the Community Score Card tool was adopted by stakeholders in tracking the implementation of ongoing projects of the Assembly. The PM&E was conducted through the channel of field visits, site meetings and stakeholder review meetings.

### 2.6.3 UPDATE ON PARTICIPATORY M&E

Annex 9: Update on Participatory Monitoring and Evaluation (PM&E) Tools Used

| Name of the PM&E Tool | Policy/Programme/Project Involved | Consultant or Resource Persons Involved | Methodology Used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Community Score Card | Ensuring affordability , equitable and easy accessibility to accommodation for the vulnerable | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and progress are appreciable | Contractors should be resourced to complete the projects to enable it serve the intended purpose. |
| Community Score Card | Ensuring affordability , equitable and easy accessibility to Universal Health Coverage | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and progress are appreciable | Contractors should be resourced to complete the projects to enable it serve the intended purpose. |
| Community Score Card | Ensuring affordability , equitable and easy accessibility to Universal Health Coverage | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and progress are appreciable | Contractors should be resourced to complete the projects to enable it serve the intended purpose. |
| Community Score Card | Ensuring affordability , equitable and easy accessibility to improved sanitation facilities for schoolchildren | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and the completion stage were acceptable. | Contractors should be paid all outstanding funds after the defect liability period. |
| Community Score Card | Ensuring safe environment and sustainable management of floods disasters and solid waste management | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and progress are appreciable | Contractors should be resourced to complete the projects to enable it serve the intended purpose. |
| Community Score Card | Ensuring accessibility and safe mobility of residents | Municipal Planning Officer and MPCU Members | Site Meetings, Stakeholder Review Meetings and Field Visits | Quality of work and completion stage were acceptable. | Contractors deserves payment given progress and quality of work done. |

Source: LaNMMA MPCU, 2025

Annex 9 outlines the Participatory Monitoring and Evaluation as tool to track project roll-out information for decision-making in respect of resource allocation and delivery benchmarks.  Quarterly participatory monitoring in exercise involving all relevant stakeholders were undertaken. The key outcome of the monitoring was the remarkable completion and usage rate of the facilities. With improved logistical support in terms of vehicles and funding a lot was achieved during the year under review.  Community stakeholder interest that has been dwindling is getting rekindled.

# CHAPTER THREE

## 3.0 INTRODUCTION

Despite the impressive progress recorded in the implementation of programmes and projects for the year under review, the Municipality encountered a great deal of challenges. However, with the support of relevant stakeholders, majority of the challenges were surmounted whilst some are in the process of being addressed.

## 3.1 KEY ISSUES ADDRESSED AND THOSE YET TO BE ADDRESSED

The Key issues addressed were as follows:

- Agreeing on appropriate indicators and setting of achievable targets in relation to goals and objectives set

- Strengthening of stakeholder involvement in monitoring and evaluation (participatory monitoring and evaluation)

- Provision of basic logistics for field work such as wellington boots, notepads, etc.

The issues yet to be addressed include:

- Difficulty in accessing data for measuring interventions implemented and for planning of future interventions

- Inadequate logistics and budget support for Monitoring and Evaluation

- Difficulty on the part of communities to release land for development projects coupled with high cost of land compensation.

- Weak institutional collaboration

- Projects awarded by Central Government without recourse to the Assembly and failure of contractors and awarding institutions to release project details

## 3.2 RECOMMENDATIONS

- Intensification of internally-generated revenue collection to make the Assembly financially independent,

- Continuous involvement of stakeholders in project/programme, identification, design, implementation, M&E to enhance projects/programme sustainability.

- Effective marketing of DMTDP to attract funding from other development partners;

- Continuous sensitization/dialogue with stakeholders to release land for development, and to protect lands the Assembly has earmarked for community projects.

- Strengthening of the Municipal Development Control task force to protect areas zoned for community projects.

- Enforcement of development rules and regulations to forestall haphazard development (building on waterways, proposed roads reservations etc.).

- Investing in data generation and management for effective development planning and development.

## 3.3 CONCLUSION

Despite the funding gaps from central government and development partners, the Assembly chalked some notable successes in the implementation of planned programmes and projects for 2025. With sustained commitment and focus, the Assembly stands a greater chance of improving its performance in 2025.

# APPENDIX 1

LA NKWANTANANG-MADINA MUNICIPAL ASSEMBLY (LaNMMA)

SUMMARY PROGRESS REPORT ON THE IMPLEMENTATION OF 2025 ANNUAL ACTION PLAN

| NO. | ACTIVITIES | PROGRESS |  |
| --- | --- | --- | --- |
|  |  | IMPLEMENTED | NOT IMPLEMENTED |
| CENTRAL ADMINISTRATION DEPARTMENT (ADMIN. WING) |  |  |  |
| 1 | Organise Statutory and Non-Statutory Meetings of the Assembly | Implemented |  |
| 2 | Support National Celebrations and Traditional Activities/ Festivals | Implemented |  |
| 3 | Support the Internal Management of the Assembly, Departments, and Protocol Services, MCE’s Engagement with the Citizenry etc. | Implemented |  |
| 4 | Support the Assembly’s Sub- Structures (Madina and Oyarifa Zonal Councils) | Implemented |  |
| 5 | Support Security Operations and Interventions in the Municipality | Implemented |  |
| 6 | Support the Functionality of Assembly’s Client Service Unit ( Production of Flyers, Fact Sheets, Service Charter etc. as Publicity Materials) | Implemented |  |
| MUNICIPAL PLANNING CO-ORDINATING UNIT |  |  |  |
| 1 | Support the Preparation of MTDP (2026-2029) and Review of the 2025 Annual Action plan of the Assembly | Implemented |  |
| 2 | Conduct Monitoring & Evaluation Activities and Stakeholder Engagement Sessions | Implemented |  |
| 3 | Co-ordinate and Support Implementation of Government Flagship Programmes | Implemented |  |
| 4 | Co-ordinate and Organise Town Hall Meetings and Stakeholder Engagements | Implemented |  |
| 5 | Support the Implementation of National Anti-Corruption Action Plan (NACAP) in the Municipality | Implemented |  |
| 6 | Support Tourism & LED Promotion Activities (Capacity, Delivery of Start-up Packages, Creation of Enabling Env. and Infrastructure Delivery | Implemented |  |
| 7 | Facilitate Climate Change and Adaptation Sensitisation for Staff, Assembly and Community Members | Implemented |  |
| MUNICIPAL BUDGET UNIT |  |  |  |
| 1 | Co-ordinate the Preparation, Review, Implementation and Performance Reporting of the Composite Budget | Implemented |  |
| 2 | Organise Stakeholders’ Consultative Engagements for the Preparation and Gazetting of Approved 2026 Fee-Fixing Document | Implemented |  |
| 3 | Co-ordinate the Preparation and Implementation of 2026 Revenue Improvement Action Plan (RIAP) | Implemented |  |
| 4 | Support the Training of Revenue Collectors | Implemented |  |
| 5 | Monitor Revenue Collection and Management | Implemented |  |
| MUNICIPAL ENVIRONMENTAL HEALTH AND SANITATION UNIT |  |  |  |
| 1 | Organize Monthly Clean-Up Exercises including National Sanitation Day, Drain Desilting and Refuse Evacuation Exercises as well as Undertake E-waste Solid and Liquid Waste Services in the Municipality | Implemented |  |
| 2 | Organize Quarterly Meetings with Waste Contractors and Supervise their Operations | Implemented |  |
| 3 | Conduct Sensitisation on WASH Activities and Support Hygiene Education and Promote Sale of Wholesome Meat and Food Items | Implemented |  |
| 4 | Establish and Finance the Activities of the Municipal Sanitation Task Force |  |  |
| 5 | Carry out Environmental Education on Noise, Air, Water, Cholera and other Communicable Diseases Including Good Sanitation Practices | Implemented |  |
| 6 | Update the Municipal Environmental Sanitation Strategy and Action Plan (MESSAP 2022-2025) | Implemented |  |
| 7 | Inspect Premises and Issue1,200 Notices of Abatement to Landlords and Occupants | Implemented |  |
| 8 | Enforce Sanitary Regulation and Prosecute Offenders | Implemented |  |
| 9 | Mark out, delineate , allocate grave spaces, supervise burials and manage the cemeteries | Implemented |  |
| 10 | Disinfest and Disinfect infected Premises and Public Places | Implemented |  |
| 11 | Support the implementation of the Sanitation Improvement Package(SIP) | Implemented |  |
| 12 | Support the implementation of the Community Led Total Sanitation (CLTS) | Implemented |  |
| 13 | Facilitate the Procurement of Personal Protective Equipment and Cleaning Materials | Implemented |  |
| 14 | Undertake Quarterly Public Sensitisation on Proper Waste Management Practices in Low-Lying Areas in order to Prevent Flooding | Implemented |  |
| 15 | Execute Air Quality Improvement Interventions in Air Pollution Hotspots in the Municipality (Public Education, Stakeholder Engagement, Arrest and Prosecution of Offenders | Implemented |  |
| MUNICIPAL PROCUREMENT UNIT |  |  |  |
| 1 | Procure Assorted Office Equipment and Accessories (Computers & Accessories, Binding Machines, Scanners, Metal Cabinets) and Furniture for Departments including Swivel Chairs) | Implemented |  |
| 2 | Procure Office Supplies and Consumables (Including Stationery, Protective and Sanitary Cleaning Materials, Logistics for Revenue Mobilisation and Operational Security Logistics ) | Implemented |  |
| 3 | Procure Vehicle Tyres and other Spare Parts for Assembly’s Fleet of Vehicles | Implemented |  |
| 4 | Procure Assorted Business Support Items and Equipment for PWDs | Implemented |  |
| 5 | Procure Assorted Items for Donations (Rice Sugar, Cooking Oil etc.) | Implemented |  |
| 6 | Procure End-of-Year Motivational Package for Staff and Assembly Members | Implemented |  |
| 7 | Procure Document Management Software, External Drives and Microsoft Windows Server and Domain for MIS and Registry | Implemented |  |
| 8 | Procure 5No. Refuse Containers for Selected Communities | Implemented |  |
| 9 | Procure Uninterrupted Power Supply (UPS) Device | Implemented |  |
| 10 | Furnishing of Storeroom for Safe Storage of Assembly’s Assets and Consumables | Implemented |  |
| INTERNAL AUDIT UNIT |  |  |  |
| 1 | Conduct Quarterly Audit of Activities of the Zonal Council, Budget Cycle Implementation, Cash Management (IGF, DACF and other Donor Funds), Procurement Management Special Audit Investigation, Revenue Management, Transport and Fuel Management and Audit of Management and Administration. | Implemented |  |
| NATIONAL YOUTH AUTHORITY |  |  |  |
| 1 | Sensitize the Youth on Mental Health Issues, ARSH Education on Teenage Pregnancy and the Effects of Abortion in young People, Drugs – Tramadol associated dangers on the youth, suicidal issues among young people. | Implemented |  |
| 2 | Promote TVET Education through Public Sensitisation | Implemented |  |
| 3 | Organize a seminar on leadership skills and accountability | Implemented |  |
| 4 | Organise Digital Marketing Training on Mobile Phone Repairs | Implemented |  |
| YOUTH EMPLOYMENT AGENCY |  |  |  |
| 1 | Recruit and Train Youth in Fire Prevention Sanitation, Community Education Teaching and School Support Programmes | Implemented |  |
| 2 | Conduct Periodic Monitoring of Beneficiaries at Work Post | Implemented |  |
| MANAGEMENT INFORMATION SYSTEM (MIS) UNIT |  |  |  |
| 1 | Collect Revenue Data, Facilitate Billing and Print Property Rate and BOP Bills for the Assembly | Implemented |  |
| 2 | Undertake General Servicing and Maintenance of the Assembly’s Computers and Accessories, the GIFMIS, Intercom Servers, and Other Devices | Implemented |  |
| 3 | Upgrade applications, Develop and Host the Assembly’s Website; Anti-Virus Software for all Official Computers and Provide Monthly Subscription for Broadband Internet Services | Implemented |  |
| DEPARTMENT OF URBAN ROADS |  |  |  |
| 1 | Facilitate the Installation of Pedestrian Crossing and Road Signs on selected Roads within the Municipality | Implemented |  |
| 2 | Grade and Maintain Selected Roads within the Municipality | Implemented |  |
| 3 | Upgrading of 3No. Roads within the Municipality(Madina Central Mosque Road, Kekele Polyclinic Road, Naa Adjeley Sowah Road | Implemented |  |
| 4 | Construct 2 Double Box Culverts on Swan Clinic Area | Implemented |  |
| 5 | Construct 3 No. Footbridges in Selected Communities | Implemented |  |
| 6 | Desilt Selected Drains in the Municipality | Implemented |  |
| 7 | Monitor and Supervise Ongoing Roads Projects in the Municipality | Implemented |  |
| 8 | Undertake Drainage Repairs and Slabs Construction | Implemented |  |
| MUNICIPAL EDUCATION DIRECTORATE/DEPT. OF EDUC YOUTH AND SPORTS |  |  |  |
| 1 | Construct 1No. 5-unit KG Block for Madina Fire Armour Basic School | Implemented |  |
| 2 | Construct 1No. Office Block with Ancillary Facilities for the Municipal Education Directorate | Implemented |  |
| 3 | Construct 1No. 3-storey 18-unit classroom block with Ancillary Facilities and 6-unit Teacher’s Accommodation for Pantang Hospital Basic School (Phase 1) | Implemented |  |
| 4 | Construct 1 No. 2-Storey 12-unit classroom block with Ancillary Facilities and 6-unit Teacher’s Accommodation for Pantang Presbyterian Basic School | Implemented |  |
| 5 | Construct 1 No. 2-Storey 12-unit classroom block with Ancillary Facilities and 6-unit Teacher’s Accommodation for Danfa Methodist Basic School (Phase 1) | Implemented |  |
| 6 | Complete 1No. 3-storey 18-unit classroom block with Ancillary Facilities and 12-unit Teacher’s Accommodation for Madina No.1 Cluster of Schools | Implemented |  |
| 7 | Procure and Distribute Assorted Furniture to Selected Schools in the Municipality | Implemented |  |
| 8 | Conduct STMIE Clinic | Implemented |  |
| 9 | Conduct & Monitor Mock Examinations for JHS 3 Students and Support for the Conduct of 2025 BECE | Implemented |  |
| 10 | Organise Orientation for Newly Trained Teachers and MDE Annual Conference (CODE) | Implemented |  |
| 11 | Support the Municipal Education Annual Review Session and Teacher Prize day | Implemented |  |
| 12 | Support Inter-Circuit Sports Festival and KG School Arts & Cultural Festival | Implemented |  |
| 13 | Observe My-First-Day at School | Implemented |  |
| 14 | Provide Support for Independence Day Celebrations and Debate for SHS | Implemented |  |
| 15 | Organise the Kiddy March Past | Implemented |  |
| 16 | Organise Career Guidance and Counselling Week Celebration | Implemented |  |
| 17 | Organise Girl Child Menstrual Hygiene Day | Implemented |  |
| 18 | Support Brilliant-But- Needy Students | Implemented |  |
| 19 | Support the Reading and Spelling Bee Competition | Implemented |  |
| NON-FORMAL EDUCATION DIVISION/CEA |  |  |  |
| 1 | Organise Functional Literacy Classes for Out of School Children and Supervise and Monitor Existing Classes | Implemented |  |
| 2 | Organise Training/ Orientation for NSS Personnel on Teaching/Facilitation Methodology | Implemented |  |
| 3 | Train 100 CEA Learners on Income Generating Activities (Soap-Making, Bleach and Beads Production) | Implemented |  |
| 4 | Undertake Health Screening | Implemented |  |
| 5 | Establish 2 Remedial Centres for Classes for JHS and SHS Drop-outs and Candidates | Implemented |  |
| MUNICIPAL HEALTH DIRECTORATE/DEPT OF HEALTH |  |  |  |
| 1 | Co-ordinate HIV & AIDs as well as TB and Malaria Related Activities within the Municipality | Implemented |  |
| 2 | Carry Out Public Education and Sensitisation on Health Issues, Celebrate National and Official Health Days and Provide Essential Health Services to Communities | Implemented |  |
| 3 | Conduct Surveys on Pertinent Health Issues | Implemented |  |
| 4 | Organise Monthly, Quarterly and Bi-Annual Performance Review Meetings | Implemented |  |
| 5 | Conduct Training for Health Officers and Facility Managers | Implemented |  |
| 6 | Embark on Quarterly Monitoring and Supervisory Visits to all Health Facilities | Implemented |  |
| 7 | Construct and Operationalize (Equip) 1No. 2-storey Multipurpose Surgical Theatre Block for Kekele Polyclinic in Madina | Implemented |  |
| 8 | Complete the Construction of 1No. CHPS Compound Block with Fence wall for Otinibi | Implemented |  |
| 9 | Furnish Oyarifa Health Centre and Construct Fence Wall for the Facility | Implemented |  |
| 10 | Procure 4No. 40-footer Containers and other equipment to support the CHPS Zones in the Municipality | Implemented |  |
| 11 | Procure Office and other Equipment to Support the CHPS Zones | Implemented |  |
| DEPARTMENT OF AGRICULTURE |  |  |  |
| 1 | Register at Least 200 Farmers on the Planting for Food and Jobs (PFJ) Programme | Implemented |  |
| 2 | Train 30 Women on Climate Smart Agriculture | Implemented |  |
| 3 | Promote the Production and Distribution of 1,000 Cockerels to improve the Nutritional Status and Incomes of Households | Implemented |  |
| 4 | Carry out One Demonstration on Backyard Vegetable Gardening | Implemented |  |
| 5 | Compile and Submit Quarterly and One Annual Technical and Financial Reports to LaNMMA & RDA | Implemented |  |
| 6 | Conduct Active Surveillance of Diseases in Poultry and Livestock | Implemented |  |
| 7 | Conduct Yield Studies for 5 Selected Crops (Maize, Pepper, Okro, Cassava & Tomato) within the Municipality | Implemented |  |
| 8 | Undertake at Least 480 Home and Farm Visits to Extend Agricultural technologies to Farmers and Follow-up on Trainings | Implemented |  |
| 9 | Conduct monitoring and evaluation on Planned Activities | Implemented |  |
| 10 | Organise 2 Technical Performance Review and 2 General Staff Meetings | Implemented |  |
| 11 | Conduct Demonstration on Value Addition and Utilization of Local Foods (Fruits and Vegetables) | Implemented |  |
| 12 | Organize 1No. District Agricultural Planning Session with Farmers and Other Stakeholders (RELC) | Implemented |  |
| 13 | Build the Capacity of 30 (11 Males and 19 Females) Poultry Farmers on Processing and Marketing | Implemented |  |
| 14 | Provide Start-Up Package for 4 Potential Fish Farmers Trained in Aquaculture | Implemented |  |
| 15 | Train 30 Market Women and Processors on Food Safety | Implemented |  |
| 16 | Organise Anti-Rabies Campaign and Vaccination | Implemented |  |
| 17 | Train 30 Staff on Post- Harvest Management Practices | Implemented |  |
| 18 | Support the Administrative Running of the Department | Implemented |  |
| 19 | Organise Municipal Farmers’ Day Celebration | Implemented |  |
| DEPARTMENT OF TRANSPORT |  |  |  |
| 1 | Undertake Transport Route Identification Exercise | Implemented |  |
| 2 | Undertake Commercial Driver License and Vehicle Sticker Enforcement Exercise | Implemented |  |
|  | Support the DRIP Initiative | Implemented |  |
| 3 | Organise Meetings with Transport Operators | Implemented |  |
| 4 | Undertake Routine Maintenance and Servicing of Assembly’s Fleet of Vehicles and Renew Insurance Policies and DVLA Roadworthy | Implemented |  |
| 5 | Procure and Distribute Fuel for Official Use | Implemented |  |
| 6 | Undertake Road Safety Activities | Implemented |  |
| HUMAN RESOURCE DEPARTMENT |  |  |  |
| 1 | Facilitate Promotion Interviews of Staff (Promotion Interview fees, Exam fees, Transport) and NALAG Activities | Implemented |  |
| 2 | Co-ordinate the Preparation, Implementation and Review of the 2025 Capacity Building Plan (CBP) of the Assembly (including training in GIFMIS for Finance Department Staff) and Submit Relevant Reports | Implemented |  |
| 3 | Support Manpower Development Workshops and Capacity Building | Implemented |  |
| 4 | Organize Quarterly Staff Durbar to Address Staff Concerns/Welfare Issues, Orientation for NSS Personnel, End –of - Service Allowance and End-of-Year Staff Motivation | Implemented |  |
| 5 | Review Staff Attendance, HRMIS and Co-ordinate Staff Monthly Salary Validation of Staff | Implemented |  |
| NATIONAL DISASTER MANAGEMENT ORGANISATION (NADMO) |  |  |  |
| 1 | Observe World Disaster Day and Undertake Public Education and Sensitisation on Disaster Risk Reduction (DRR) | Implemented |  |
| 2 | Organise Workshops for Traditional Authorities and Real Estate Developers on Adverse Effects of Building on Waterways as Climate Change Impact Mitigation Response | Implemented |  |
| 3 | Engage in Flood Mitigation Measures (Dredging of Selected Drains) | Implemented |  |
| 4 | Organize Community Fora on Fire Disasters for Selected Farmers/Stakeholders | Implemented |  |
| 5 | Profile Disaster Cases and Distribute Relief Items to Victims and Carry out Disaster Response/ Rescue | Implemented |  |
| DEPARTMENT OF CO-OPERATIVES/TRADE AND INDUSTRY |  |  |  |
| 1 | Train 15 Co-operative Societies within the Municipality | Implemented |  |
| 2 | Sensitize 4 communities on the importance of co-operatives | Implemented |  |
| 3 | Audit of 6No. Credit Unions and 2No. Transport Societies | Implemented |  |
| 4 | Register 6No. Co-operative Groups in Madina | Implemented |  |
| 5 | Facilitate Capacity Building of SMEs and Connect them to Soft Loans and Support AfCFTA Initiatives/Interventions in the Municipality | Implemented |  |
| 6 | Monitor the operations of MSMEs | Implemented |  |
| PHYSICAL PLANNING DEPARTMENT |  |  |  |
| 1 | Organise 12No. Technical Sub-committee/Spatial Planning Committee Meetings | Implemented |  |
| 2 | Support the Implementation of Street Naming and Property Addressing Project | Implemented |  |
| 3 | Prepare Spatial Development Framework (SDF) and Structural Plans for the Municipality | Implemented |  |
| 4 | Support 2 Officers to Undertake Training in Physical Development Management | Implemented |  |
| 5 | Sensitize Developers on Permit Acquisition Procedure and the need to plant a minimum of 6 trees on their land | Implemented |  |
| 6 | Support Green Ghana Day Tree Planting and Carry Out Routine Horticultural Maintenance Works | Implemented |  |
| 7 | Conduct Active Garden Maintenance Culture (Watering, Mulching, Manure, Staking, Replacement, Planting, etc) | Implemented |  |
| 8 | Facilitate Community Engagement in Conversation and Restoration Efforts | Implemented |  |
| WORKS DEPARTMENT |  |  |  |
| 1 | Support Development Control Activities (Including Decongestion of Selected Areas) | Implemented |  |
| 2 | Install, Repair and Replace Streetlights in Selected Communities | Implemented |  |
| 3 | Undertake Rehabilitation and Maintenance of Assembly’s Assets and Other Public Buildings | Implemented |  |
| 4 | Support the Implementation of the MP’s Development Projects and Programmes | Implemented |  |
| 5 | Support Self-Help Projects /Counterpart Funded Projects of Communities | Implemented |  |
| 6 | Construct 1 No. Mini-Market for Pantang Aboman Comm. (Old Refuse Dump Site) | Implemented |  |
| 7 | Construct 1 No. Storey Office Accommodation with Conference Hall and Ancillary Facilities for Oyarifa Zonal Council (Phase 1) | Implemented |  |
| 8 | Construct 1No. Ultra-Modern 24-Hour Economy Market at Madina Abokobi Station/Madina Market | Implemented |  |
| 9 | Drill and Mechanize 14 No. Boreholes and Facilitate Borehole Water Extension for Selected Communities | Implemented |  |
| DEPARTMENT OF SOCIAL WELFARE AND COMMUNITY DEVELOPMENT |  |  |  |
| 1 | Re-Unify 15 Children in Need of Care and Protection with their Families (Missing and Abandoned Children) | Implemented |  |
| 2 | Monitor the Activities of 20 NGOs, 80 Day Care Centres and 2 RHCs | Implemented |  |
| 3 | Conduct Follow-ups on Child Maintenance, Family Welfare and Custody Cases | Implemented |  |
| 4 | Support Case Management and Strengthen Referrals and Linkages | Implemented |  |
| 5 | Facilitate the Payment of Cash Grant to LEAP Beneficiaries and Register them onto the NHIS | Implemented |  |
| 6 | Organise Disability Fund Management Committee Meetings Quarterly and Conduct Skills Training for PWDs | Implemented |  |
| 7 | Collaborate with GES to educate Parents and Students on Adolescent Health | Implemented |  |
| 8 | Engage with Schoolchildren and Communities using the CP Toolkit | Implemented |  |
| 9 | Facilitate the Dissemination of Development-Related Information (on Sanitation, Health, BOP, Tax Payment etc. ) to Improve the Well-being of the Populace | Implemented |  |
| 10 | Support and Promote Child Protection Activities (Adolescent, Mental Health, Well-being, Child Labour, SGBV School Re-entry Policy of Teenage Mothers) Among Comm. Members | Implemented |  |
| 11 | Transfer Sustainable and Employable/ Artisanal Skills to Women and Youth to Reduce Unemployment in the Municipality. | Implemented |  |
| 12 | Provide Business Advisory, Skills Training and Other Support Services in the Municipality | Implemented |  |
| 13 | Partner other Organisations to Promote Gender Mainstreaming-Related Activities/Programmes | Implemented |  |
| 14 | Organize Gender Sensitization Programme on Spousal Right, Adolescent Reproduction Health and Career Guidance | Implemented |  |
| FINANCE DEPARTMENT |  |  |  |
| 1 | Prepare and Submit Monthly, Quarterly and Annual Financial Statements | Implemented |  |
| 2 | Co-ordinate and Conduct Revenue Monitoring and Review Revenue Performance | Implemented |  |
| 3 | Validate Receivables and Fixed Asset Register | Implemented |  |
| 4 | Undertake Data Collection on BOP and Property Rate | Implemented |  |
| INFORMATION SERVICES DEPARTMENT |  |  |  |
| 1 | Disseminate Information on Government Policies and Programmes and Print Out Brochures & Flyers | Implemented |  |
| 2 | Facilitate Media Publicity and Press Coverage on the Assembly and MCE’s Engagement with Communities | Implemented |  |
| DEPARTMENT OF STATISTICS |  |  |  |
| 1 | Compile and Administrative Data for the Assembly (i.e. Data on Health, Forestry, Agriculture, Education, Electricity, Road Accidents, Improved Sanitation, Birth, Death, Assembly’s Revenue , LED Indicators, Water and SDG Budget | Implemented |  |
| 2 | Conduct Monthly Market Surveys and Co-ordinate National Surveys on Prices of Goods and Services | Implemented |  |
| NATIONAL COMMISSION FOR CIVIC EDUCATION (NCCE) |  |  |  |
| 1 | Promote Civil Society Participation in the Democratic Processes and Development in the Municipality ( Media, Religious Bodies) | Implemented |  |
| 2 | Conduct Public Education on NACAP and Social Auditing | Implemented |  |
| 3 | Organise Civic Education Club Activities and Senior Citizens Interactions with Selected School Children | Implemented |  |
| 4 | Support the Green Ghana Activities | Implemented |  |
| BIRTHS AND DEATHS REGISTRY |  |  |  |
| 1 | Educate the Public on the Importance of Birth and Death Registration and Organise Mass Registration of Infant Births Under One year | Implemented |  |